Prepared By: Team TriTechPlus

Hazel Grace P. Gamalo 
Lancine Diare

July E. Asuncion 
Patricia Mae R. De Lima

Sheanne Jennica P. Guantero

Prepared By: Team TriTechPlus

Hazel Grace P. Gamalo 
Lancine Diare

July E. Asuncion 
Patricia Mae R. De Lima

Sheanne Jennica P. Guantero

INDIRECTLY AIDS:

INDIRECTLY AIDS:

CONTRIBUTES TO:

CONTRIBUTES TO:

RAMS Flex

RAMS Flex

ITRO Equipment Borrowing and Return Tracking

Asia Pacific College (APC) — Information Technology Resource Office (ITRO)

ITRO Equipment Borrowing and Return Tracking

Asia Pacific College (APC) — Information Technology Resource Office (ITRO)

AY 2026-2027

# TABLE OF CONTENTS

1. Company Profile	6

1.1 Company Background	6

1.2 Mission	6

1.3 Vision	6

2. Initiation	6

2.1 Project Charter	6

Purpose	6

Deliverables	6

High-Level Risks, Assumptions, and Constraints	7

Milestone Schedule	7

Budget Summary	8

Signatures	1

2.2 Business Case	8

2.3 Project Brief	8

2.4 Stakeholder Management Strategy	9

2.5 Stakeholder Analysis	9

Power / Interest Grid	9

Detailed Stakeholder Table	9

2.6 Statement of Work (SOW)	10

2.7 Business Model Canvas	10

2.8 Feasibility Study	1

3. Planning	12

3.1 Communications Management Plan	12

3.1.1 Communication Management Approach	12

3.1.2 Project Team Directory	12

3.1.3 Communication Matrix	12

3.1.4 Guidelines for Meetings	13

3.1.5 Communication Escalation Process	13

3.2 Scope Management Plan	13

3.2.1 Scope Management Approach	13

3.2.2 Roles and Responsibilities	14

3.2.3 Scope Definition	14

3.2.4 Project Exclusions	15

3.2.5 Product Acceptance Criteria	15

3.2.6 Scope Verification and Control	16

3.3 Work Breakdown Structure (WBS)	16

3.3.1 Outline View	16

3.3.2 Tabular Structure	17

3.3.3 Tree Structure	18

3.3.4 WBS Dictionary	19

3.4 Schedule Management Plan	21

3.4.1 Schedule Management Approach	21

3.4.2 Schedule Milestones	21

3.4.3 Schedule Control and Thresholds	22

3.4.4 Rules of Performance Measurement	22

3.4.5 Detailed Schedule	22

3.4.6 Actual Sprint, Site Visit, and UAT Timeline Alignment Record	23

3.5 Quality Management Plan	23

3.5.1 Quality Management Approach	23

3.5.2 Quality Requirements and Standards	23

3.5.3 Quality Assurance (QA)	23

3.5.4 Quality Control (QC)	23

3.5.5 Defect Classification and Management	24

3.5.6 Quality Metrics	25

3.6 Cost Management Plan	25

3.6.1 Cost Management Approach	25

3.6.2 Cost Estimation Methodology	26

3.6.3 Project Budget Estimate	26

3.6.4 Measuring Project Costs (EVM)	28

3.6.5 Cost Variance Response Process	29

3.7 Human Resource Plan	30

3.7.1 Roles and Responsibilities	30

3.7.2 Project Organizational Charts	30

3.7.3 Staffing Management	31

3.8 Risk Management Plan	31

3.8.1 Risk Management Approach	31

3.8.2 Risk Rating Definitions	31

3.8.3 Priority Score Matrix	31

Bands: 1–4 Low · 5–10 Medium · 11–15 High · 16–25 Critical	32

3.8.5 Risk Monitoring and Escalation	32

3.9 Requirements Management Plan	32

3.9.1 Requirements Management Approach	32

3.9.2 Requirements Prioritization Process (MoSCoW)	32

3.9.3 Requirements Traceability Matrix	33

3.10 Risk Register	35

3.11 Configuration Management Plan	36

3.11.1 Configuration Management Approach	36

3.11.2 Configuration Item Control	36

3.12 Change Management Plan	37

3.12.1 Change Management Approach	37

3.12.2 Change Control Board (CCB)	37

3.12.3 Change Classification Tiers	37

3.12.4 Change Control Process	37

3.12.5 Change Log	38

4. Execution	40

4.1 Sprint 1 (Aug 28 – Sep 1, 2026)	40

4.2 Sprint 2 (Sep 1 – Sep 4, 2026)	40

4.3 Sprint 3 (Sep 4 – Sep 8, 2026)	41

4.4 Sprint 4 (Sep 8 – Sep 11, 2026)	41

4.5 Sprint 5 (Sep 11 – Sep 15, 2026)	42

4.6 Sprint 6 (Sep 15 – Sep 18, 2026)	42

4.7 Sprint 7 (Sep 18 – Sep 22, 2026)	43

4.8 Sprint 8 (Sep 22 – Sep 25, 2026)	43

4.9 Sprint 9 (Sep 25 – Sep 29, 2026)	43

4.10 Sprint 10 (Sep 29 – Oct 2, 2026)	44

4.11 Sprint 11 (Oct 2 – Oct 6, 2026)	44

4.12 Sprint 12 (Oct 6 – Oct 9, 2026)	45

5. Agile	45

5.1 Agile Team Charter	45

5.2 Agile Team Values	46

6. Project Documents	46

6.1 System Design Document	46

Core Entities (proposed — confirm against actual schema)	47

Core Workflow Sequence (high level)	48

7. Monitoring and Controlling	49

7.1 Development baseline status	49

7.2 Documentation status	49

7.3 Meeting effort and combined labor baseline	49

8. Closing	50

8.1 Transition Out Plan	50

8.2 Project Acceptance	50

8.3 Post Project Review Template	50

8.4 Lessons Learned	51

Appendices	51

Appendix A: Methodology	51

Appendix B: Detailed Schedule	51

Appendix C: Detailed Cost Estimates	51

Appendix D: Jira Work Packages	51

Appendix E: Change Request Form	57

Appendix F: Project Acceptance Form	58

Appendix G: Links	58

Appendix H Review Findings Log updated 10 October 2026	58

# 1. Company Profile

## 1.1 Company Background

Asia Pacific College (APC) is a Philippine higher-education institution that positions itself as a bridge between academe and industry through programs founded on information-technology concepts and applications. The client context for this project is APC's Information Technology Resource Office (ITRO), which supports institutional technology-resource needs. RAMS Flex is a proposed academic prototype intended for ITRO workflow review, not an official APC operational system.

## 1.2 Mission

APC states that it aims to provide the business and information and communications technology industry in the Philippines and the global community with lifelong-learning graduates anchored in integrity and professionalism.

## 1.3 Vision

APC envisions itself as a preferred higher-education institution bridging academe and industry through IT-based programs guided by integrity, industry, and innovation.

# 2. Initiation

## 2.1 Project Charter

### Purpose

RAMS Flex is an academic web-based prototype that demonstrates a centralized workflow for the borrowing and return of equipment managed by ITRO. It provides a simulated, controlled environment where the proposed workflow can be reviewed, tested, and refined without using real APC or ITRO personal, equipment, or transaction data. RAMS Flex is strictly an academic prototype and  does not have authorization for live deployment or integration with APC's production systems.

### Deliverables

- Working web-based prototype / MVP (PHP/MySQL on Apache, hosted on AWS Lightsail) covering authentication and roles, asset catalog and eligibility, borrowing-ticket lifecycle, AI chatbot self-service, custody, overdue management, reporting and audit

- Simulated equipment catalogue, prioritized toward cameras/video equipment and laptops/webcams/clickers

- Test cases, test results and defect log; UAT sign-off sheet

- User guide and technical documentation

- Source-code repository

- Complete project-management documentation (this document), including the Jira-aligned WBS, Requirements Traceability Matrix, risk register, change log and defect log (Jira project RFD)

### High-Level Risks, Assumptions, and Constraints

| Assumptions | Constraints |
| --- | --- |
| Team has access to computers, internet, Jira, GitHub, and required tools | Fixed 6-week schedule: August 28 – October 9, 2026 |
| ITRO stakeholder will provide feedback on the prototype (requirements, sprint demonstrations, and UAT results) when available | Fixed five-member team; capacity follows confirmed DEV allocations plus DOCS and meetings |
| Simulated accounts/data are acceptable for demonstration provided they meet the Product Acceptance Criteria (Section 3.2.5); the Product Owner and the ITRO stakeholder verify at UAT that the simulated data is realistic and consistent with the ITRO borrowing workflow | Prototype only — no production integration |
| Chosen stack (PHP/MySQL/AWS Lightsail) supports required functions | Limited budget — mainly free/existing tools |

Top risks are summarized here and detailed fully in the Risk Register (Section 3.10), which now mirrors the 26 Jira Risk issues (RFD-514 to RFD-539). The highest-priority risks are incorrect eligibility rules approving unauthorized borrowers (RFD-521) and critical defects remaining near the final deadline (RFD-534), both scored 15-High; 9 further risks score 12-High, covering unvalidated APC procedures, eligibility-rule variation, unavailable APC APIs or test environments, stale or double-counted inventory, report accuracy, UAT participation, and delayed final acceptance.

### Milestone Schedule

| Milestone | Target Date | Owner |
| --- | --- | --- |
| Charter and workflow confirmation (Sprint 1: RFD-472–474) | Aug 28, 2026 | Hazel Gamalo / Lancine Diare |
| Requirements, WBS, RACI, Jira backlog baseline (Sprints 1–2: RFD-472–478) | Sep 4, 2026 | Sheanne Guantero / Hazel Gamalo |
| Architecture, data model, identity mapping, wireframes/prototype (Sprints 3–4: RFD-479–485) | Sep 11, 2026 | Patricia De Lima / July Asuncion |
| Engineering setup, authentication, asset records and catalog (Sprints 5–6: RFD-486–492) | Sep 18, 2026 | Lancine Diare / Patricia De Lima / July Asuncion |
| Eligibility, ticket creation/tracking and chatbot (Sprints 7–8: RFD-493–499) | Sep 25, 2026 | Patricia De Lima / July Asuncion |
| Release, return, closure, overdue and reporting build (Sprints 9–10: RFD-500–506) | Oct 2, 2026 | Sheanne Guantero / Hazel Gamalo |
| Audit, verification testing, UAT, deployment, handover, final submission (Sprints 11–12: RFD-507–513) | Oct 9, 2026 | Entire team |

### Budget Summary

Revised planned budget: PHP 491,979.90, comprising PHP 422,011.26 simulated academic labor, PHP 5,797.35 retained infrastructure assumptions, PHP 42,780.86 contingency and PHP 21,390.43 management reserve. Confirmed effort is 588 DEV hours, 141.75 DOCS hours and 206.25 meeting student-hours, totaling 936 hours. This correction establishes the planning figures; it does not certify actual expenditure or stakeholder acceptance.

## 2.2 Business Case

Problem Statement: ITRO currently coordinates equipment borrowing through separate messages, manual forms, and an Excel-based inventory. This fragments visibility of request status, approvals, equipment condition, and availability across multiple untracked channels.

Anticipated Outcomes: A working, demonstrable prototype covering the full request-to-closure lifecycle, giving ITRO and academic evaluators a concrete artifact to review.

Recommendation: Build a controlled, simulated-data prototype rather than doing nothing or purchasing commercial asset-management software — see the alternatives analysis below.

| Option | Description | Assessment |
| --- | --- | --- |
| Do nothing | Continue with Excel + paper forms | Low cost, but leaves the visibility problem unsolved, accountability is also difficult to prove. |
| Buy commercial asset-management software | License an existing inventory/asset system | Cost and integration risk not justified before workflow is validated |
| Build a simulated prototype (selected) | Team builds a controlled, simulated-data prototype to validate the workflow first | Selected academic prototype; revised planned total PHP 491,979.90. Simulated labor and retained infrastructure estimates are detailed in Section 3.6.3. |

Strategic Alignment: Supports APC's emphasis on academic excellence, industry-oriented learning, and practical experience in requirements analysis, Agile development, and project management.

## 2.3 Project Brief

RAMS Flex is a simulated-data academic prototype system for ITRO, demonstrating a centralized digital workflow for equipment borrowing and return — covering request, approval, release, return, and closure. Target users are four simulated roles: borrowers (students/faculty borrowing equipment), custodians (approving, releasing, and receiving returned equipment), administrators (managing assets, rules, and configuration), and auditors (reviewing audit records and reports). The project supersedes the team's original proposal, "CampusFlow: AI Campus Service Hub" — a broader, AI-driven ticketing platform spanning IT support, registrar, guidance, and facilities — narrowed via CR-01 (Section 3.12.5) down to this single, well-defined workflow so a five-person student team can deliver a complete, tested prototype in six weeks. Following the Jira re-baseline (CR-02, Section 3.12.5), the scope also covers eligibility evaluation, overdue management with a controlled clearance referral, reporting and audit, and a limited AI chatbot for self-service and ticket escalation.

## 2.4 Stakeholder Management Strategy

The strategy identifies the internal team (Team TriTechPlus), academic oversight (Sponsor, Adviser, PROJMAN Instructor), and the external ITRO stakeholder (Ms. Grace Ann P. Morte), with an engagement plan moving each stakeholder from their current to their desired engagement level.

- Internal – Project Team: Hazel Gamalo, Lancine Diare, July Asuncion, Patricia De Lima, Sheanne Guantero

- Internal – Academic Oversight: Jojo Castillo, Carl Dominique Bueno, Felino Calderon III

- External – ITRO Stakeholder: Ms. Grace Ann P. Morte

- External – Indirect/Future End Users: simulated borrowers, custodians, administrators, and auditors

## 2.5 Stakeholder Analysis

### Power / Interest Grid

| Stakeholder | Power | Interest | Classification |
| --- | --- | --- | --- |
| Jojo Castillo (Sponsor) | High | High | Manage Closely |
| Carl Dominique Bueno (Adviser) | High | High | Manage Closely |
| Felino Calderon III (Instructor) | High | Moderate | Keep Satisfied |
| Grace Ann P. Morte (ITRO) | Moderate | Moderate | Keep Informed |
| Hazel Gamalo (PM) / Sheanne Guantero (PO) | High | High | Manage Closely |
| Development Team | Low | High | Keep Informed / Involve |
| Simulated End Users | Low | High | Keep Informed |

### Detailed Stakeholder Table

| Stakeholder | Interests | Influence | Engagement Strategy |
| --- | --- | --- | --- |
| Sponsor (Jojo) | Strategic relevance, final acceptance | Approves major decisions & scope changes | Briefed at each milestone; final demo sign-off |
| Adviser (Carl) | Feasibility, methodology quality | Co-approves major changes (CCB) | Reviews plans at each planning gate |
| Instructor (Felino) | Academic/PROJMAN compliance | Grades required deliverables | Reviews submitted documentation |
| ITRO ( Morte) | Workflow accuracy, real-world fit | Validates workflow & UAT | Scheduled consultation, ≥1 week lead time |
| Dev Team | Clear requirements, sustainable pace | Implements scope, flags issues | Daily standups, sprint ceremonies |

## 2.6 Statement of Work (SOW)

Project title: RAMS Flex — ITRO Equipment Borrowing and Return Tracking  Prototype.

Scope of work: Team TriTechPlus will design, develop, test, and document a simulated-data web prototype covering the full equipment lifecycle (request → review → approval/decline → release → return → availability update → closure), built on PHP/MySQL hosted on AWS Lightsail (Monolithic architecture), using an Agile methodology with task tracking using Jira within a fixed 6-week schedule.

Period of performance: August 28, 2026 – October 9, 2026.

Place of performance: Remote/online (student team); cloud-hosted on AWS Lightsail.

Work requirements: See High-Level Requirements (Section 2.1) and Scope Definition (Section 3.2.3).

Acceptance: Per the Product Acceptance Criteria (Section 3.2.5) and formal Sponsor sign-off at final demonstration.

Exclusions: No production deployment, no real data, no payment processing, no native mobile app (Section 3.2.4).

## 2.7 Business Model Canvas

| Block | Content |
| --- | --- |
| Key Partners and Suppliers | Partners: APC ITRO, Project Adviser/PROJMAN faculty. Suppliers: AWS (Lightsail, paid instance), Atlassian (Jira, paid seats) |
| Key Activities | Requirements gathering, software development, testing, documentation, stakeholder validation |
| Key Resources | 5-person student dev team, Jira/GitHub/Teams, AWS Lightsail instance, ITRO domain knowledge (via Ms. Morte) |
| Value Propositions | A risk-free, simulated-data prototype proving a centralized borrowing workflow is viable before ITRO commits real budget or data |
| Customer Relationships | Direct consultation with ITRO stakeholder; sprint reviews and demos with Sponsor/Adviser |
| Channels | Awareness: APC student portal/LMS announcements, orientation materials, and campus signage Evaluation: browse-only equipment catalogue showing availability, specifications, and borrowing terms; display at the ITRO office Reservation: RAMS Flex web booking portal (request, review, and approval) Delivery: equipment release and pickup at the ITRO front desk After-sales: email reminders before the due date; ITRO support email/helpdesk for returns, extensions, and damaged-equipment reports Project delivery: live demonstrations, UAT sessions, and submitted documentation |
| Customer Segments | ITRO staff/administrators; student and faculty equipment requesters (students borrowing cameras/video gear; classes borrowing laptops/webcams/clickers) |
| Cost Structure | Simulated DEV labor PHP 264,575.80 + DOCS PHP 64,549.12 + meetings PHP 92,886.34; infrastructure PHP 5,797.35; contingency PHP 42,780.86; management reserve PHP 21,390.43. |
| Revenue Streams | Not applicable — academic prototype; the "return" is validated learning and a decision-ready concept for ITRO, not revenue |

## 2.8 Feasibility Study

| Dimension | Assessment |
| --- | --- |
| Technical Feasibility | High — PHP/MySQL/AWS Lightsail is a well-understood, low-complexity stack matching the team's skill set; Monolithic architecture fits prototype scale. Also, the lending/borrowing business process is well established and many models exist. |
| Schedule Feasibility | Requires calendar reconciliation. The confirmed 588 DEV hours replace the retired 300-hour capacity assumption; include 141.75 DOCS hours and 206.25 meeting student-hours when assessing availability. |
| Financial Feasibility | High — real infrastructure cost is modest (₱5,797.35 for AWS Lightsail + Jira over the project duration); simulated labor has no real cash outlay |
| Operational Feasibility | Moderate — depends on ITRO stakeholder availability for workflow/condition-check validation; mitigated via early, scheduled consultation |
| Regulatory/Compliance Feasibility | High — simulated data only avoids Data Privacy Act (RA 10173) exposure; no production system integration required |
| Overall Conclusion | Feasible — risks are manageable within the Risk Register (Section 3.10) and do not threaten project viability |

# 3. Planning

## 3.1 Communications Management Plan

### 3.1.1 Communication Management Approach

RAMS Flex uses a Hybrid Agile communication strategy: informal, high-frequency communication (daily standups, Jira comments) for coordination, and formal, scheduled communication (milestone reports, sponsor briefings) for governance and academic accountability.

### 3.1.2 Project Team Directory

| Role | Name | Organization | Email |
| --- | --- | --- | --- |
| PM / Scrum Master | Hazel Grace P. Gamalo | Team TriTechPlus | hazel.gamalo@apc.edu.ph |
| Developer Lead / PM | Lancine Diare | Team TriTechPlus | lancine.diare@apc.edu.ph |
| Frontend Developer | July E. Asuncion | Team TriTechPlus | july.asuncion@apc.edu.ph |
| Backend Developer / PM | Patricia Mae R. De Lima | Team TriTechPlus | patricia.delima@apc.edu.ph |
| Product Owner / QA | Sheanne Jennica P. Guantero | Team TriTechPlus | sheanne.guantero@apc.edu.ph |
| Sponsor | Jojo Castillo | APC – ITRO | jojo.castillo@apc.edu.ph |
| Adviser | Carl Dominique Bueno | APC | carl.bueno@apc.edu.ph |
| Instructor | Felino Calderon III | APC | felino.calderon@apc.edu.ph |
| ITRO Stakeholder | Ms. Grace Ann P. Morte | APC – ITRO | graceann.morte@apc.edu.ph |

Emails follow the team's standard APC-domain placeholder convention; confirm actual addresses before circulation.

### 3.1.3 Communication Matrix

| Type | Objective | Medium | Frequency | Audience | Owner |
| --- | --- | --- | --- | --- | --- |
| Daily Standup | Progress / blockers | MS Teams | Daily | Team | Hazel |
| Sprint Review | Demo, verify criteria | Teams / Jira | End of sprint | Team, Sponsor, Adviser | Hazel |
| Sprint Retrospective | Process improvement | MS Teams | End of sprint | Team | Hazel |
| Milestone Report | Status vs. baseline | Email / document | Per milestone | Sponsor, Adviser, Instructor | Hazel |
| ITRO Consultation | Workflow validation | Meeting / email | As available | Ms. Morte, PO | Sheanne |

### 3.1.4 Guidelines for Meetings

- Agendas shared at least 24 hours ahead for any formal meeting; daily standups are exempt and follow a fixed 3-question format.

- Standups are time-boxed to 15 minutes; longer discussions are taken offline immediately after.

- Meeting minutes/notes are published within 24 hours after any formal meeting.

- Every formal meeting ends with clear action items and owners, not just discussion.

### 3.1.5 Communication Escalation Process

| Priority | Trigger | Authority | Response Time |
| --- | --- | --- | --- |
| P1 – Critical | Blocker threatening final submission | Sponsor | Within 4 hours |
| P2 – High | Milestone at risk beyond 3-day threshold | Adviser → Sponsor | Within 1 business day |
| P3 – Normal | Routine clarification needed | PM / PO | Within 2 business days |

## 3.2 Scope Management Plan

### 3.2.1 Scope Management Approach

Scope is defined in the Charter (Section 2.1) and decomposed in Jira project RFD into 9 Epics (E2–E10, RFD-463 to RFD-471), each with Stories and companion Tasks (21 Stories, 21 Tasks) broken into 105 Subtasks. Risks, change candidates, and defects are tracked as Jira Risk (RFD-514–539), Change (RFD-540–547) and Bug (RFD-548–578) issues. The PO maintains backlog priority; the PM maintains the scope baseline and change log.

### 3.2.2 Roles and Responsibilities

| Role | Responsibility | Authority |
| --- | --- | --- |
| PM (Hazel) | Maintains baseline, backlog structure, change log | Primary scope-control authority |
| PO (Sheanne) | Defines/prioritizes backlog, writes acceptance criteria | Approves story-level scope |
| Sponsor (Jojo) | Confirms business relevance, final acceptance | Approves major scope changes |
| Adviser (Carl) | Reviews feasibility/methodology | Co-approves major changes (CCB) |
| Dev Team | Implements scope, flags ambiguities | Recommends, no approval authority |

### 3.2.3 Scope Definition

Project scope: Plan, design, develop, test, and document a simulated-data prototype for the ITRO equipment lifecycle using Agile Scrum (Jira) within a predictive baseline.

Confirmed technical architecture: PHP/MySQL, hosted on a single AWS Lightsail instance (Monolithic LAMP pattern: Ubuntu + Apache + PHP + MySQL) with a Static IP. Provisioned from the pre-configured LAMP blueprint with baseline firewall rules (ports 80, 443, and 22 restricted to developer IPs; no public database access). Role-based access (borrower, custodian, administrator, auditor) is modeled on LDAP directory concepts, with APC identity and eligibility attributes mapped so the design can support a future APC SSO; no live APC directory connection is made.

Product scope — what RAMS Flex delivers:

- Full simulated lifecycle: Catalog → Eligibility Check → Borrowing Ticket → Custodian Approval/Rejection → Release with Acknowledgment → Return Inspection → Availability Update → Closure and Reconciliation, with ticket tracking and history

- Asset catalog with asset types, categories and individual asset units (condition, status, archive rules), searchable by borrowers and weighted toward confirmed high-volume items: cameras/photography-video equipment, laptops, webcams, and clickers (classes)

- Preparation/inspection checklist, borrower acknowledgment and condition recording at release and return, digitizing ITRO's current Excel + paper-form practice into structured fields

- Configurable eligibility evaluation (role, program, status, asset) with a displayed decision reason, followed by custodian approval; release/return inspected by the equipment custodian. Multi-level approval for selected asset categories is a registered change candidate (RFD-543), not baseline scope

- Simulated role-based authentication and access control (LDAP-concept modeled, not a real directory connection) for borrower, custodian, administrator, and auditor roles

- Overdue detection, daily reminders with history, a custodian overdue queue, and a controlled clearance referral/export (a documented referral, not a live APC integration)

- KPI dashboard, report/export views, and an audit trail of critical transactions with administration controls

- Limited AI chatbot for borrower self-service, restricted to approved sources with confidence and fallback rules, escalating unanswered queries to a ticket routed to the appropriate department (RFD-498/499)

### 3.2.4 Project Exclusions

- Live/production deployment or integration with real APC/ITRO systems

- Real student, employee, borrower, staff, or inventory data

- Actual LDAP integration with APC's real directory service

- Direct integration with APC Sirius or clearance systems (integration points are documented only; manual/mock fallback and controlled export are provided)

- Migration of ITRO's existing Excel inventory or paper borrower's form

- Barcode/RFID/QR scanning or physical asset-tagging hardware (QR/barcode scanning is a registered change candidate, RFD-544)

- Automated/AI-based physical damage detection

- Payments, deposits, or damage-fee processing

- Equipment procurement, repair, or physical handling

- Native mobile applications; multi-campus/multi-branch tracking

- Post-project maintenance or hosting renewal beyond October 9, 2026

### 3.2.5 Product Acceptance Criteria

| Deliverable | Criteria | Authority |
| --- | --- | --- |
| Asset catalog, eligibility & ticket module (E4–E5) | Catalog covers high-volume categories; ineligible requests blocked server-side with decision reason; unique ticket numbers; 0 critical defects | Sheanne (PO) |
| Approval & custody workflow (E5–E6) | Authorized custodian approval/rejection; release with acknowledgment; end-to-end without unresolved critical defects | Sheanne (PO) |
| Release/return & condition-check module (E6) | Condition status + notes recorded; availability updates exactly once; damaged/lost assets never reappear as available | Ms. Morte + PO |
| Overdue management & clearance referral (E7) | Due dates and overdue cases correct; one reminder per day; referral/export limits personal data and is labeled a referral | Sheanne (PO) |
| Reporting, audit & administration (E8) | KPI totals match source records; audit trail captures critical transactions; role-restricted access | PM + PO |
| AI chatbot self-service (E5) | Answers only from approved sources; unanswered queries escalate with context to the right department; privacy preserved | Sheanne (PO) |
| Simulated authentication & roles (E3) | Role restrictions enforced correctly (positive and negative tests) | PM + PO |
| Full lifecycle demo & deployment (E9–E10) | End-to-end, no unresolved critical defects; deployed environment passes smoke test | Sponsor |
| Documentation & repository (E10) | User, administrator and technical manuals complete; code, migrations, test evidence and deployment records archived | Instructor |

### 3.2.6 Scope Verification and Control

Each Jira story/epic is checked against written acceptance criteria at sprint review, with PO sign-off before "Done." The backlog is locked after the planning baseline; any new request requires a Jira Change issue and CCB approval before entering the backlog (Section 3.12.4). Pre-identified change candidates are RFD-540 to RFD-547.

## 3.3 Work Breakdown Structure (WBS)

This WBS is aligned 1:1 to Jira project RFD (Epics RFD-463 to RFD-471, i.e. E2–E10). Each Story and Task is a work package numbered n.k within its epic (n = epic number); its Subtasks are numbered n.k.1, n.k.2, … and are listed in Appendix D. Epic E1 (initiation and planning) has no Jira key in the export; its project-management deliverables are this document’s Sections 2–3. Sprint (12 sprints, S1–S12), hour and owner assignments are proposed and should be confirmed in Jira.

### 3.3.1 Outline View

0. RAMS Flex MVP

2  Requirements and Product Design  [Jira Epic RFD-463 — Sprints 1–3]

2.1  Document the current borrowing experience  [RFD-472 Story — 3 subtasks]

2.2  Create the current-state process map  [RFD-473 Task — 2 subtasks]

2.3  Define the future borrowing-ticket lifecycle  [RFD-474 Story — 3 subtasks]

2.4  Produce future-state workflow artifacts  [RFD-475 Task — 2 subtasks]

2.5  Approve the system requirements  [RFD-476 Story — 3 subtasks]

2.6  Build the Requirements Traceability Matrix  [RFD-477 Task — 2 subtasks]

2.7  Validate the role-based user experience  [RFD-478 Story — 3 subtasks]

2.8  Conduct prototype evaluation  [RFD-479 Task — 2 subtasks]

3  Architecture and Engineering  [Jira Epic RFD-464 — Sprints 3–6]

3.1  Select an appropriate hosting architecture  [RFD-480 Story — 3 subtasks]

3.2  Create Architecture Decision Record  [RFD-481 Task — 2 subtasks]

3.3  Establish the RAMS Flex data model  [RFD-482 Story — 3 subtasks]

3.4  Produce database specifications  [RFD-483 Task — 2 subtasks]

3.5  Define secure role and identity mapping  [RFD-484 Story — 3 subtasks]

3.6  Prepare integration specifications  [RFD-485 Task — 2 subtasks]

3.7  Establish collaborative source control  [RFD-486 Story — 3 subtasks]

3.8  Configure development and test environments  [RFD-487 Task — 2 subtasks]

3.9  Authenticate users and enforce roles  [RFD-488 Story — 3 subtasks]

3.10  Test authentication and authorization  [RFD-489 Task — 2 subtasks]

4  Asset Catalog and Eligibility  [Jira Epic RFD-465 — Sprints 6–7]

4.1  Maintain asset records  [RFD-490 Story — 3 subtasks]

4.2  Validate asset data  [RFD-491 Task — 2 subtasks]

4.3  Browse and search available assets  [RFD-492 Story — 3 subtasks]

4.4  Verify catalog accuracy and usability  [RFD-493 Task — 2 subtasks]

4.5  Evaluate borrower eligibility  [RFD-494 Story — 3 subtasks]

4.6  Test eligibility scenarios  [RFD-495 Task — 2 subtasks]

5  Borrowing Ticket Lifecycle  [Jira Epic RFD-466 — Sprint 8]

5.1  Create a borrowing ticket  [RFD-496 Story — 3 subtasks]

5.2  Implement borrower ticket tracking  [RFD-497 Task — 2 subtasks]

5.3  Use an AI chatbot for self-service support and ticket escalation  [RFD-498 Story — 3 subtasks]

5.4  Implement chatbot escalation rules and safeguards  [RFD-499 Task — 2 subtasks]

6  Inventory and Asset Custody  [Jira Epic RFD-467 — Sprints 9–10]

6.1  Release an approved asset  [RFD-500 Story — 3 subtasks]

6.2  Test release controls  [RFD-501 Task — 2 subtasks]

6.3  Process asset return  [RFD-502 Story — 3 subtasks]

6.4  Close and reconcile borrowing records  [RFD-503 Task — 2 subtasks]

7  Notifications and Overdue Management  [Jira Epic RFD-468 — Sprint 10]

7.1  Monitor overdue borrowing  [RFD-504 Story — 3 subtasks]

7.2  Implement clearance referral and export  [RFD-505 Task — 2 subtasks]

8  Administration, Audit and Reporting  [Jira Epic RFD-469 — Sprints 10–11]

8.1  Monitor asset-borrowing performance  [RFD-506 Story — 3 subtasks]

8.2  Implement audit records and administration controls  [RFD-507 Task — 2 subtasks]

9  Quality Assurance and Verification  [Jira Epic RFD-470 — Sprints 11–12]

9.1  Verify end-to-end borrowing operations  [RFD-508 Story — 3 subtasks]

9.2  Conduct integration and compatibility testing  [RFD-509 Task — 2 subtasks]

9.3  Obtain user acceptance evidence  [RFD-510 Story — 3 subtasks]

9.4  Complete security and privacy verification  [RFD-511 Task — 2 subtasks]

10  Deployment, Handover and Closure  [Jira Epic RFD-471 — Sprint 12]

10.1  Deploy and accept the RAMS Flex MVP  [RFD-512 Story — 3 subtasks]

10.2  Complete technical handover and release documentation  [RFD-513 Task — 2 subtasks]

### 3.3.2 Tabular Structure

| WBS / Jira Epic | Work Package | Sprint | Items | Owner (Epic Lead, proposed) |
| --- | --- | --- | --- | --- |
| 2 / RFD-463 | E2 – Requirements and Product Design | Sprints 1–3 | 8 work packages (RFD-472–479); 20 subtasks (579–598) | Sheanne (PO) |
| 3 / RFD-464 | E3 – Architecture and Engineering | Sprints 3–6 | 10 work packages (RFD-480–489); 25 subtasks (599–623) | Lancine (Tech Lead) |
| 4 / RFD-465 | E4 – Asset Catalog and Eligibility | Sprints 6–7 | 6 work packages (RFD-490–495); 15 subtasks (624–638) | July |
| 5 / RFD-466 | E5 – Borrowing Ticket Lifecycle | Sprint 8 | 4 work packages (RFD-496–499); 10 subtasks (639–648) | Lancine (Tech Lead) |
| 6 / RFD-467 | E6 – Inventory and Asset Custody | Sprints 9–10 | 4 work packages (RFD-500–503); 10 subtasks (649–658) | Patricia |
| 7 / RFD-468 | E7 – Notifications and Overdue Management | Sprint 10 | 2 work packages (RFD-504–505); 5 subtasks (659–663) | Lancine (Tech Lead) |
| 8 / RFD-469 | E8 – Administration, Audit and Reporting | Sprints 10–11 | 2 work packages (RFD-506–507); 5 subtasks (664–668) | Hazel (PM) |
| 9 / RFD-470 | E9 – Quality Assurance and Verification | Sprints 11–12 | 4 work packages (RFD-508–511); 10 subtasks (669–678) | Sheanne (PO/QA) |
| 10 / RFD-471 | E10 – Deployment, Handover and Closure | Sprint 12 | 2 work packages (RFD-512–513); 5 subtasks (679–683) | Hazel (PM) |

### 3.3.3 Tree Structure

Figure 2. RAMS Flex Work Breakdown Structure — Jira-Aligned Tree View (Project RFD)

### 3.3.4 WBS Dictionary

| Jira ID | WBS ID | Type | Work Package | Deliverable | Owner (proposed) |
| --- | --- | --- | --- | --- | --- |
| RFD-472 | 2.1 | Story | Document the current borrowing experience | Stakeholder interview guide, consultation record, pain-point and control-gap analysis | Hazel |
| RFD-473 | 2.2 | Task | Create the current-state process map | Reviewed current-state process map with responsible actors | Hazel |
| RFD-474 | 2.3 | Story | Define the future borrowing-ticket lifecycle | Borrowing lifecycle, statuses, exceptions, escalation paths and transition rules | Hazel / Sheanne |
| RFD-475 | 2.4 | Task | Produce future-state workflow artifacts | Future-state BPMN/process diagram validated with stakeholders | Hazel / Sheanne |
| RFD-476 | 2.5 | Story | Approve the system requirements | Prioritized functional, non-functional and data requirements | Sheanne / Hazel |
| RFD-477 | 2.6 | Task | Build the Requirements Traceability Matrix | Baselined Requirements Traceability Matrix (requirements to epics, stories, designs, tests) | Sheanne / Hazel |
| RFD-478 | 2.7 | Story | Validate the role-based user experience | Borrower, custodian and administrator wireframes; clickable prototype | July |
| RFD-479 | 2.8 | Task | Conduct prototype evaluation | Prototype evaluation results and revised prototype | July / Sheanne |
| RFD-480 | 3.1 | Story | Select an appropriate hosting architecture | Hosting comparison and component, security, backup and maintenance design | Lancine |
| RFD-481 | 3.2 | Task | Create Architecture Decision Record | Architecture Decision Record with logical and deployment diagrams, approval status and open questions | Lancine / Hazel |
| RFD-482 | 3.3 | Story | Establish the RAMS Flex data model | Entities, business rules, conceptual/logical ERD, normalized relationships | Patricia |
| RFD-483 | 3.4 | Task | Produce database specifications | Data dictionary, constraints, initial MySQL schema and seed-data plan | Patricia |
| RFD-484 | 3.5 | Story | Define secure role and identity mapping | Role permission matrix, APC identity/eligibility attributes, access-denial rules | Lancine |
| RFD-485 | 3.6 | Task | Prepare integration specifications | Sirius and clearance integration specifications; manual/mock fallback and controlled export design | Patricia / Lancine |
| RFD-486 | 3.7 | Story | Establish collaborative source control | Secured GitHub repository, branching/review conventions, Jira-linked commits and PRs | Hazel |
| RFD-487 | 3.8 | Task | Configure development and test environments | PHP/MySQL development and test environments; test database and configuration guide | Patricia / Lancine |
| RFD-488 | 3.9 | Story | Authenticate users and enforce roles | Login, logout, session handling, user-role mapping, protected role routes | Lancine |
| RFD-489 | 3.10 | Task | Test authentication and authorization | Positive/negative RBAC tests and access-control results | Sheanne |
| RFD-490 | 4.1 | Story | Maintain asset records | Asset-type, category and asset-unit management with condition, status and archive rules | Patricia |
| RFD-491 | 4.2 | Task | Validate asset data | Server-side validation and uniqueness rules; initial asset test data | Patricia / July |
| RFD-492 | 4.3 | Story | Browse and search available assets | Responsive catalog with search, filter, pagination, availability and borrowing requirements | July |
| RFD-493 | 4.4 | Task | Verify catalog accuracy and usability | Catalog results verified against database records; responsive and usability check results | Sheanne |
| RFD-494 | 4.5 | Story | Evaluate borrower eligibility | Configurable eligibility rules, evaluation service, displayed result and decision reason | Patricia |
| RFD-495 | 4.6 | Task | Test eligibility scenarios | Role/program/status/asset test cases; bypass-prevention and decision-log verification | Sheanne |
| RFD-496 | 5.1 | Story | Create a borrowing ticket | Request cart, validation of asset/dates/quantity/eligibility, ticket number and submission record | Lancine / July |
| RFD-497 | 5.2 | Task | Implement borrower ticket tracking | My Requests and ticket-detail views; duplicate/invalid request test results | July |
| RFD-498 | 5.3 | Story | Use an AI chatbot for self-service support and ticket escalation | Student chatbot interface, unanswered-query detection, escalated ticket creation and routing | Lancine |
| RFD-499 | 5.4 | Task | Implement chatbot escalation rules and safeguards | Approved-source, confidence and fallback rules; escalation, privacy and access-control tests | July / Lancine |
| RFD-500 | 6.1 | Story | Release an approved asset | Preparation/inspection checklist, release with borrower acknowledgment, custody transaction and availability update | Patricia |
| RFD-501 | 6.2 | Task | Test release controls | Approved/rejected/unavailable test cases; ticket-transaction-inventory reconciliation | Sheanne |
| RFD-502 | 6.3 | Story | Process asset return | Return inspection, condition recording, availability restoration, damaged/lost/incomplete-return paths | Patricia |
| RFD-503 | 6.4 | Task | Close and reconcile borrowing records | Closure rules, transaction history, inventory reconciliation tests | Patricia / Lancine |
| RFD-504 | 7.1 | Story | Monitor overdue borrowing | Due-date calculation, overdue detection, daily reminders with history, custodian overdue queue | Lancine |
| RFD-505 | 7.2 | Task | Implement clearance referral and export | Controlled overdue referral/export; escalation, acknowledgment and reminder-failure tests | Patricia / July |
| RFD-506 | 8.1 | Story | Monitor asset-borrowing performance | Approved KPI definitions, dashboard queries, filters and report/export views | July |
| RFD-507 | 8.2 | Task | Implement audit records and administration controls | Critical-event audit records and administration controls; audit search, access and report tests | Patricia / July |
| RFD-508 | 9.1 | Story | Verify end-to-end borrowing operations | Executed authentication, catalog, eligibility, request, approval, release, return, overdue, reporting and audit test results | Sheanne |
| RFD-509 | 9.2 | Task | Conduct integration and compatibility testing | Integrity, responsiveness and browser-compatibility results; defect log, retests, updated RTM | Sheanne |
| RFD-510 | 9.3 | Story | Obtain user acceptance evidence | UAT plan, scripts and participants; UAT results and acceptance sign-off | Sheanne / Hazel |
| RFD-511 | 9.4 | Task | Complete security and privacy verification | Security (authN/authZ, validation, session) and privacy verification; release-blocking defects closed | Lancine |
| RFD-512 | 10.1 | Story | Deploy and accept the RAMS Flex MVP | Production-like environment, deployment checklist, smoke test, final demonstration and acceptance evidence | Lancine / Hazel |
| RFD-513 | 10.2 | Task | Complete technical handover and release documentation | User, administrator and technical manuals; archive of code, migrations, test evidence and deployment records | Hazel / Patricia |

## 3.4 Schedule Management Plan

### 3.4.1 Schedule Management Approach

The project schedule is encoded in Jira project RFD, which serves as our single source of truth. The fixed 6-week window (Aug 28 – Oct 9, 2026) is divided into 12 short sprints alternating Friday–Tuesday (4 days) and Tuesday–Friday (3 days); the 9 Jira Epics (E2–E10) span sprints and every Story and Task is planned into exactly one sprint (Section 4). Dependencies use Finish-to-Start issue links; the Jira Timeline (Roadmap) view serves as the Gantt-equivalent.

### 3.4.2 Schedule Milestones

| Milestone | Target Date | Sprint | Phase |
| --- | --- | --- | --- |
| Charter / Initial Documentation (Sprint 1 start; RFD-472–474) | Aug 28, 2026 | Sprint 1 | Planning |
| Requirements, WBS, RACI, Backlog (Sprints 1–2: RFD-472–478) | Sep 4, 2026 | Sprint 2 | Planning |
| Architecture, data model, identity mapping, integration specs, prototype evaluation (Sprints 3–4: RFD-479–485) | Sep 11, 2026 | Sprint 4 | Design |
| Engineering setup, authentication, asset records, catalog (Sprints 5–6: RFD-486–492) | Sep 18, 2026 | Sprint 6 | Development |
| Catalog verification, eligibility, ticket creation/tracking, chatbot (Sprints 7–8: RFD-493–499) | Sep 25, 2026 | Sprint 8 | Development |
| Release, return, closure, overdue management, clearance referral, KPI reporting (Sprints 9–10: RFD-500–506) | Oct 2, 2026 | Sprint 10 | Development |
| Audit/administration, end-to-end verification, UAT, security/privacy, deployment, handover, submission (Sprints 11–12: RFD-507–513) | Oct 9, 2026 | Sprint 12 | Testing & Closure |

### 3.4.3 Schedule Control and Thresholds

| Threshold | Trigger | Authority |
| --- | --- | --- |
| Overall baseline | Slip > 10% (~4 days) | Sponsor |
| Major milestone | Delivery moves > 3 days | CCB |
| Minor task | Delivery moves ≤ 2 days | PM (logged, no CR required) |

### 3.4.4 Rules of Performance Measurement

Progress uses a 0/100 acceptance rule at the lowest non-overlapping work-package level: 0% until the deliverable is accepted; 100% after acceptance evidence is linked. In Progress and Done statuses alone do not establish earned value. Weekly EVM uses budgeted hours multiplied by the confirmed member rate (Section 3.6.4).

### 3.4.5 Detailed Schedule

| Sprint | Activity | Duration | Dates |
| --- | --- | --- | --- |
| Sprint 1 | Document the current borrowing experience; Create the current-state process map; Define the future borrowing-ticket lifecycle (RFD-472–474) | 4 days | Aug 28 – Sep 1 |
| Sprint 2 | Produce future-state workflow artifacts; Approve the system requirements; Build the Requirements Traceability Matrix; Validate the role-based user experience (RFD-475–478) | 3 days | Sep 1 – Sep 4 |
| Sprint 3 | Conduct prototype evaluation; Select an appropriate hosting architecture; Create Architecture Decision Record (RFD-479–481) | 4 days | Sep 4 – Sep 8 |
| Sprint 4 | Establish the RAMS Flex data model; Produce database specifications; Define secure role and identity mapping; Prepare integration specifications (RFD-482–485) | 3 days | Sep 8 – Sep 11 |
| Sprint 5 | Establish collaborative source control; Configure development and test environments; Authenticate users and enforce roles (RFD-486–488) | 4 days | Sep 11 – Sep 15 |
| Sprint 6 | Test authentication and authorization; Maintain asset records; Validate asset data; Browse and search available assets (RFD-489–492) | 3 days | Sep 15 – Sep 18 |
| Sprint 7 | Verify catalog accuracy and usability; Evaluate borrower eligibility; Test eligibility scenarios (RFD-493–495) | 4 days | Sep 18 – Sep 22 |
| Sprint 8 | Create a borrowing ticket; Implement borrower ticket tracking; Use an AI chatbot for self-service support and ticket escalation; Implement chatbot escalation rules and safeguards (RFD-496–499) | 3 days | Sep 22 – Sep 25 |
| Sprint 9 | Release an approved asset; Test release controls; Process asset return (RFD-500–502) | 4 days | Sep 25 – Sep 29 |
| Sprint 10 | Close and reconcile borrowing records; Monitor overdue borrowing; Implement clearance referral and export; Monitor asset-borrowing performance (RFD-503–506) | 3 days | Sep 29 – Oct 2 |
| Sprint 11 | Implement audit records and administration controls; Verify end-to-end borrowing operations; Conduct integration and compatibility testing (RFD-507–509) | 4 days | Oct 2 – Oct 6 |
| Sprint 12 | Obtain user acceptance evidence; Complete security and privacy verification; Deploy and accept the RAMS Flex MVP; Complete technical handover and release documentation (RFD-510–513) | 3 days | Oct 6 – Oct 9 |

### 3.4.6 Actual Sprint, Site Visit, and UAT Timeline Alignment Record

| Planned Item | Planned Date | Actual/Confirmed Date | Note |
| --- | --- | --- | --- |
| Architecture finalization | Sep 11, 2026 | — |  |
| ITRO Site Visit / Stakeholder Consultation | Within Sprints 5–8 (Sep 11 – Sep 25) | — | Pending confirmation of Ms. Morte's availability |
| UAT Session | Sprints 11–12: Oct 2–9, 2026 | — |  |

## 3.5 Quality Management Plan

### 3.5.1 Quality Management Approach

Prevention-over-inspection: quality is built into Scrum's Definition of Done (code review, testing, acceptance criteria) rather than treated as a separate phase.

### 3.5.2 Quality Requirements and Standards

- Republic Act 10173 (Data Privacy Act) principles — design-level, not certified

- OWASP Top 10 — secure-coding baseline

- ISO/IEC 25010 — informal reference framework

- APC PROJMAN course rubric — the binding academic standard

### 3.5.3 Quality Assurance (QA)

Proactive, process-level activities: peer code review before every merge, database schema validation before design lock, and adherence to the Definition of Done at each sprint.

### 3.5.4 Quality Control (QC)

Reactive, inspection-level activities: unit testing, integration testing (end-to-end workflow), role-access testing, and User Acceptance Testing (UAT) against scripted borrowing scenarios.

### 3.5.5 Defect Classification and Management

| Severity | Definition | Resolution |
| --- | --- | --- |
| Critical | Crash, data loss, security bypass | Resolve before UAT sign-off |
| Major | Feature broken, workflow not fully blocked | Resolve within the sprint |
| Minor | Cosmetic or low-impact issue | Resolve when time allows, tracked in backlog |

Defect Log. Defects are recorded as Jira Bug issues (RFD-548 to RFD-578, 31 bugs). Severity below is proposed under the classification above; each bug is linked to a requirement in the RTM (Section 3.9.3) and is retested under RFD-509 / RFD-673. Live status is tracked in Jira.

| Jira ID | Defect (Bug) | Epic | Severity | Requirement |
| --- | --- | --- | --- | --- |
| RFD-548 | Prototype permits bypass of a required workflow step | E2 | Critical | REQ-05, REQ-07 |
| RFD-549 | Prototype navigation or labels conflict with approved terminology | E2 | Minor | REQ-NFR-02 |
| RFD-550 | Database constraint permits invalid borrowing data | E3 | Major | REQ-NFR-03 |
| RFD-551 | Application configuration exposes secrets or environment details | E3 | Critical | REQ-NFR-01 |
| RFD-552 | User accesses a route outside the assigned role | E3 | Critical | REQ-01 |
| RFD-553 | Archived asset appears in the borrower catalog | E4 | Major | REQ-02, REQ-03 |
| RFD-554 | Eligibility result conflicts with configured rule | E4 | Major | REQ-04 |
| RFD-555 | Catalog quantity conflicts with inventory records | E4 | Major | REQ-03 |
| RFD-556 | Ineligible user submits a borrowing ticket | E5 | Critical | REQ-04, REQ-05 |
| RFD-557 | Duplicate ticket number is generated | E5 | Major | REQ-05 |
| RFD-558 | Unauthorized user approves or rejects a ticket | E5 | Critical | REQ-07 |
| RFD-559 | Ticket enters an invalid lifecycle status | E5 | Major | REQ-05, REQ-06 |
| RFD-560 | Inventory is reduced before physical release | E6 | Major | REQ-09, REQ-11 |
| RFD-561 | Available quantity becomes negative | E6 | Critical | REQ-11 |
| RFD-562 | Return restores the wrong asset unit or quantity | E6 | Major | REQ-10 |
| RFD-563 | Lost or damaged asset appears available | E6 | Critical | REQ-10 |
| RFD-564 | Reminder is sent before the due date | E7 | Major | REQ-13 |
| RFD-565 | Duplicate daily reminders are generated | E7 | Minor | REQ-13 |
| RFD-566 | Returned ticket remains overdue | E7 | Major | REQ-12, REQ-13 |
| RFD-567 | Referral export exposes unnecessary personal information | E7 | Critical | REQ-14 |
| RFD-568 | Dashboard total conflicts with source records | E8 | Major | REQ-15 |
| RFD-569 | Unauthorized role accesses management reports | E8 | Critical | REQ-15, REQ-01 |
| RFD-570 | Critical transaction is missing from the audit trail | E8 | Major | REQ-16 |
| RFD-571 | Critical end-to-end borrowing scenario fails | E9 | Critical | REQ-05 to REQ-12 |
| RFD-572 | Broken access control permits unauthorized action | E9 | Critical | REQ-01, REQ-NFR-01 |
| RFD-573 | Invalid input produces an unhandled server error | E9 | Major | REQ-NFR-01 |
| RFD-574 | Layout is unusable on a supported mobile viewport | E9 | Minor | REQ-NFR-02 |
| RFD-575 | UAT action creates inconsistent ticket and inventory records | E9 | Critical | REQ-12 |
| RFD-576 | Deployed application cannot connect to the database | E10 | Critical | REQ-NFR-04 |
| RFD-577 | Environment configuration causes broken links or missing resources | E10 | Major | REQ-NFR-04 |
| RFD-578 | Deployment package omits a required migration or configuration file | E10 | Major | REQ-NFR-04 |

### 3.5.6 Quality Metrics

| Metric | Target | Method | Owner |
| --- | --- | --- | --- |
| UAT First-Pass Rate | ≥ 90% | Tally per test case | Sheanne |
| Critical Defects at Demo | 0 | Jira count | Hazel |
| Code Review Coverage | 100% of merges reviewed | GitHub PR log | Lancine |

## 3.6 Cost Management Plan

### 3.6.1 Cost Management Approach

Bottom-up planning uses three separate labor categories: development, documentation and meetings. All categories use the member rates confirmed on 10 October 2026. Academic labor is simulated costing, not payroll expenditure. Infrastructure values are retained planning assumptions and must be confirmed before purchase. PHP, MySQL and Apache have no software license charge in this model.

Deviation handling (SOP). The approved budget in Section 3.6.3 is the cost baseline. When a deviation occurs, such as a new feature request, a team member leaving, or a cost or schedule variance flagged in the weekly EVM review, the team follows the procedure below. It is run through the Change Management Plan (Section 3.12).

1. Log. The PM records the trigger as a Jira Change Request with its own CR ID.

2. Assess. The PM and team estimate the added or lost effort in hours at the member rates in Section 3.6.3, plus any added infrastructure cost. For a new feature, the cost is the extra build, test, and documentation hours. When a member leaves, the remaining work is reassigned or the role is backfilled, and the cost is the extra hours at that role's rate.

3. Decide and fund. A deviation that fits inside the Contingency Reserve (10% of direct costs) is approved by the CCB. One that needs the Management Reserve (5% of direct costs) requires CCB and Sponsor approval. If the reserves are not enough, the Sponsor either approves additional budget or the CCB removes lower-priority backlog items to stay within the baseline.

4. Update and report. After approval, the PM updates the cost baseline, the Jira backlog, and the EVM sheet, and reports the change at the next sprint review.

Usage and data growth. RAMS Flex is web-based, so its running cost grows with the number of users and the size of the database, not only with the features built. For the prototype, usage is limited to simulated accounts and data, and the Lightsail instance in Section 3.6.3 (1 GB RAM, 40 GB SSD, 2 TB transfer) is sufficient. The team will review CPU, memory, disk use, and data transfer monthly. If a live deployment is ever approved, ITRO must re-estimate the recurring costs: a larger Lightsail instance, extra storage, automated backups and snapshots, data transfer above the included allowance, and more Jira seats. These costs are outside this project's budget and require a separate approval.

### 3.6.2 Cost Estimation Methodology

Labor is estimated from the confirmed work allocation: 588 DEV subtask hours, 141.75 DOCS leaf-work hours and 206.25 meeting student-hours. Multiply each member’s planned hours by that member’s confirmed rate. Do not add story or parent-task estimates to the same subtask effort. Meetings are counted once per student attending: 41.25 hours each for five students.

Infrastructure values below are the existing document’s two-month cost assumptions, retained for comparability. They are estimates rather than verified current vendor quotations. Reconfirm the plan, duration, exchange rate and actual charges before committing funds.

### 3.6.3 Project Budget Estimate

Confirmed DEV Labor Estimate

| Team member and role focus | DEV hours | Rate per hour | DEV planned cost |
| --- | --- | --- | --- |
| Hazel Grace Gamalo PM / Scrum Master / QA | 116 | PHP 478.50 | PHP 55,506.00 |
| July Asuncion Frontend Developer / PM | 116 | PHP 400.00 | PHP 46,400.00 |
| Lancine Diare Developer Lead / PM | 120 | PHP 468.75 | PHP 56,250.00 |
| Patricia Mae De Lima Backend Developer / PM | 120 | PHP 373.29 | PHP 44,794.80 |
| Sheanne Jennica Guantero Product Owner / QA / PM | 116 | PHP 531.25 | PHP 61,625.00 |
| TOTAL | 588 |  | PHP 264,575.80 |

| Team member | DOCS hours | Meeting hours | Total hours | Total labor cost |
| --- | --- | --- | --- | --- |
| Hazel Grace Gamalo | 31.00 | 41.25 | 188.25 | PHP 90,077.63 |
| July Asuncion | 22.0 | 41.25 | 179.25 | PHP 71,700.00 |
| Lancine Diare | 32.75 | 41.25 | 194.00 | PHP 90,937.50 |
| Patricia Mae De Lima | 26.50 | 41.25 | 187.75 | PHP 70,085.20 |
| Sheanne Jennica Guantero | 29.50 | 41.25 | 186.75 | PHP 99,210.94 |
| TOTAL | 141.75 | 206.25 | 936 | PHP 422,011.26 |

| DEV team member | Tasks | Subtasks | Task story points |
| --- | --- | --- | --- |
| Hazel Grace Gamalo | 4 | 20 | 31 |
| July Asuncion | 4 | 20 | 29 |
| Lancine Diare | 4 | 20 | 32 |
| Patricia Mae De Lima | 5 | 25 | 29 |
| Sheanne Jennica Guantero | 4 | 20 | 26 |
| TOTAL | 21 | 105 | 147 |

| Labor category | Planned hours | Planned cost |
| --- | --- | --- |
| DEV | 588 | PHP 264,575.80 |
| DOCS | 141.75 | PHP 64,549.12 |
| Meetings | 206.25 | PHP 92,886.34 |
| TOTAL | 936 | PHP 422,011.26 |

DOCS allocation comes from native estimates on leaf issues in RAMS Flex Docs (2).csv: Hazel 31.00 h; July 22.00 h; Lancine 32.75 h; Patricia 26.50 h; Sheanne 29.50 h. The parent estimate on RFT-233 is excluded. Meeting allocation follows the supplied recurring schedule, including 55 stand-ups, 11 adviser meetings and 11 retrospectives. Instructor and adviser effort is excluded. Totals use unrounded calculations; displayed member costs may differ by PHP 0.01 due to rounding.

Infrastructure and Tooling Estimate — Retained Planning Assumptions

| Item | Pricing Basis | Qty × Duration | Cost (USD) | Cost (PHP) |
| --- | --- | --- | --- | --- |
| AWS Lightsail instance (Apache + PHP + MySQL host) | $10.00/mo — 1 GB RAM / 2 vCPU / 40 GB SSD / 2 TB transfer tier | 1 instance × 2 mo | $20.00 | ₱1,170.00 |
| Jira Software — Standard plan | $7.91/user/mo (retained estimate) | 5 users × 2 mo | $79.10 | ₱4,627.35 |
| PHP, MySQL, Apache (software itself) | Open-source — no license fee | — | $0.00 | ₱0.00 |
| GitHub (private repos), MS Teams | Free tier — retained assumption for a 5-person team | — | $0.00 | ₱0.00 |
| Subtotal (Infrastructure & Tooling) |  |  | $99.10 | ₱5,797.35 |

| Item | Basis | Amount |
| --- | --- | --- |
| DEV labor | 588 h at confirmed member rates | PHP 264,575.80 |
| DOCS labor | 141.75 h at confirmed member rates | PHP 64,549.12 |
| Meeting labor | 206.25 student-hours | PHP 92,886.34 |
| Total labor | 936 planned hours | PHP 422,011.26 |
| Infrastructure and tooling | Existing two-month assumptions | PHP 5,797.35 |
| Direct costs | Labor + infrastructure | PHP 427,808.61 |
| Contingency reserve | 10% of direct costs | PHP 42,780.86 |
| Cost baseline including contingency | Direct costs + contingency | PHP 470,589.47 |
| Management reserve | 5% of direct costs; outside cost baseline | PHP 21,390.43 |
| Total planned budget | Direct costs + both reserves | PHP 491,979.90 |

### 3.6.4 Measuring Project Costs (EVM)

EVM is tracked separately for DEV, DOCS and meetings using the same confirmed rates. PV is the budgeted labor cost of work scheduled by the reporting date; EV is the budgeted labor cost of accepted deliverables; AC is verified worklog hours multiplied by the applicable member rate. Story points are not currency and are not directly multiplied into EV. Use the 0/100 acceptance rule: no value before acceptance; full budgeted value after reviewed evidence is retained.

Formulas: PV = sum of scheduled work-package budgets; EV = sum of accepted work-package budgets; AC = sum of verified actual hours × member rate; CV = EV − AC; SV = EV − PV; CPI = EV / AC; SPI = EV / PV; EAC = AC + revised remaining-cost estimate; ETC = EAC − AC; VAC = BAC − EAC; TCPI = (BAC − EV) / (BAC − AC). Do not calculate ratios with zero denominators or forecast from unvalidated data. The labor BAC excludes infrastructure and reserves; compare labor PV, EV and AC on the same basis.

EVM inputs — revised planning baseline dated 10 October 2026

| Input | Confirmed planning value |
| --- | --- |
| DEV labor BAC | PHP 264,575.80 |
| DOCS labor BAC | PHP 64,549.12 |
| Meeting labor BAC | PHP 92,886.34 |
| Combined labor BAC | PHP 422,011.26 |
| Confirmed planned effort | 936 hours |
| EVM scope | Labor only; infrastructure and reserves tracked separately |
| Reporting basis | Approved dated work-package schedule and accepted deliverables |
| Actual cost basis | Verified worklogs by member; meeting attendance reconciled |

EVM reporting position — actual performance requires verified evidence

| Measure | Current reporting position |
| --- | --- |
| BAC — labor | PHP 422,011.26 |
| PV | Pending a reconciled time-phased schedule |
| EV | Pending acceptance evidence; not inferred from Done counts |
| AC | Pending verified worklogs and meeting attendance |
| CV and SV | Not calculated until PV, EV and AC are verified |
| CPI and SPI | Not calculated until valid inputs and nonzero denominators exist |
| EAC and ETC | Re-estimate remaining work after verified actuals |
| VAC and TCPI | Calculate after the revised forecast is established |

Baseline reconciliation and reporting controls

| Control | Required action |
| --- | --- |
| Hours and rates | Use the user-confirmed 588 / 141.75 / 206.25 h and rates; align Jira estimates before EVM reporting |
| DEV assignment | 116 h Hazel; 116 h July; 120 h Lancine; 120 h Patricia; 116 h Sheanne |
| DOCS effort | Count leaf work once; exclude overlapping parent estimates |
| Meetings | Count 41.25 h per student; reconcile attendance with logged effort |
| Acceptance | Attach evidence before claiming EV |
| Historical EVM | Superseded results from the old labor baseline are withdrawn |

### 3.6.5 Cost Variance Response Process

| Condition | Trigger | Action |
| --- | --- | --- |
| Healthy | CPI/SPI ≥ 0.95 | Monitor only |
| Caution | CPI/SPI 0.80–0.94 | PM investigates, adjusts task allocation |
| Critical | CPI/SPI < 0.80 | Escalate to Adviser/Sponsor; consider re-scoping via CCB |
| Additional (added) | CPI or SPI > 1.20 | Audit time logs and Jira status history before reporting; do not use for forecasting until validated |

## 3.7 Human Resource Plan

### 3.7.1 Roles and Responsibilities

| Role | Name | Skills | Responsibility |
| --- | --- | --- | --- |
| PM / Scrum Master | Hazel Gamalo | Scheduling, risk mgmt, Jira, facilitation | Execution, tracking, communication |
| Developer Lead / PM | Lancine Diare | PHP, MySQL, AWS Lightsail, security | Architecture, backend, code review |
| Frontend Dev | July Asuncion | HTML/CSS/JS, UI/UX | Interface design/development |
| Backend Developer / PM | Patricia De Lima | PHP/MySQL, DB integration | Schema, catalogue, integration |
| PO / QA | Sheanne Guantero | Requirements, testing, UAT | Backlog, acceptance, defects |

### 3.7.2 Project Organizational Charts

Figure 1. RAMS Flex Project Organizational Chart

RACI Matrix (Key Deliverables):

| Deliverable | PM (Hazel) | PO (Sheanne) | Dev Team | Sponsor / Adviser |
| --- | --- | --- | --- | --- |
| Project Charter and planning documents (E1) | A | C | I | R |
| Requirements & Backlog (E2) | A | R | C | I |
| Architecture, Data Model & Engineering Setup (E3) | I | A | R | I |
| Catalog, Eligibility, Ticket, Custody Development (E4–E6) | I | A | R | I |
| Overdue, Reporting & Audit Development (E7–E8) | I | A | R | I |
| Quality Assurance & Verification (E9) | I | A | R | I |
| UAT, Deployment & Final Demonstration (E9–E10) | R | A | C | A |

R = Responsible, A = Accountable, C = Consulted, I = Informed.

### 3.7.3 Staffing Management

Employment Model: simulated academic labor costing using the user-confirmed rates. Actual labor cost for EVM requires verified member-level worklogs; planned hours do not establish actual expenditure.

Resource Calendars: DEV allocation is Hazel 116 h, July 116 h, Lancine 120 h, Patricia 120 h and Sheanne 116 h. DOCS adds 141.75 team hours; meetings add 41.25 h per member. Validate availability against the reconciled implementation calendar; the retired 60-hour-per-member model is no longer used.

Training & Development: Lancine — 2 hrs self-study on Lightsail LAMP provisioning/firewalls before Sprint 1; team — 1 hr shared walkthrough on simulated role-access concepts before Sprint 5 (Sep 11); Sheanne/Hazel — 1 hr on Jira Timeline/burndown reporting before Sprint 1.

Recognition & Rewards: Peer evaluation rubric each sprint retrospective (feeds academic grading); informal "MVP of the Sprint" recognition at sprint review.

## 3.8 Risk Management Plan

### 3.8.1 Risk Management Approach

Qualitative analysis: Probability × Impact (1–5 scale each) → Priority Score. Each risk is recorded as a Jira Risk issue and mirrored in the Risk Register (Section 3.10). Reviewed weekly alongside schedule/cost at sprint review.

### 3.8.2 Risk Rating Definitions

Probability: 1 Very Low (rare) → 5 Very High (almost certain). Impact: 1 Insignificant (negligible) → 5 Severe (catastrophic/threatens submission).

### 3.8.3 Priority Score Matrix

| Prob \ Impact | 1 | 2 | 3 | 4 | 5 |
| --- | --- | --- | --- | --- | --- |
| 5 | 5-Med | 10-Med | 15-High | 20-Crit | 25-Crit |
| 4 | 4-Low | 8-Med | 12-High | 16-Crit | 20-Crit |
| 3 | 3-Low | 6-Med | 9-Med | 12-High | 15-High |
| 2 | 2-Low | 4-Low | 6-Med | 8-Med | 10-Med |
| 1 | 1-Low | 2-Low | 3-Low | 4-Low | 5-Med |

Bands: 1–4 Low · 5–10 Medium · 11–15 High · 16–25 Critical

3.8.4 Risk Categories

- Technical  ·  Schedule  ·  Resource/Team Capacity  ·  Stakeholder/Communication

- Scope  ·  Data Privacy & Security  ·  Financial/Budget  ·  External/Academic

### 3.8.5 Risk Monitoring and Escalation

Reviewed weekly at sprint review alongside schedule/cost. New High-scoring risks are flagged to the Adviser; Critical risks or materialized issues escalate immediately to the Sponsor within the same 4-hour P1 window as the Communications Plan.

## 3.9 Requirements Management Plan

### 3.9.1 Requirements Management Approach

Requirements originate from the Charter and stakeholder consultation, are written as Jira stories with explicit acceptance criteria, and are locked into the backlog baseline after planning (Section 3.2.6). Any new or changed requirement must go through the Change Control Process (Section 3.12.4). Each requirement is traced in the RTM (Section 3.9.3) to its design, build and verification issues, to its Jira risks, defects and change candidates.

### 3.9.2 Requirements Prioritization Process (MoSCoW)

| Priority | Requirement Examples |
| --- | --- |
| Must Have | Authentication and role-based access; asset records; eligibility evaluation; borrowing ticket creation; custodian approval/rejection; release with acknowledgment; return with condition inspection; automatic availability update; closure and reconciliation |
| Should Have | Asset browse/search; ticket tracking (My Requests); overdue detection with daily reminders; clearance referral/export; audit trail; responsive interface |
| Could Have | AI chatbot self-service and escalation; KPI dashboards and report/export views; UI polish beyond core wireframes |
| Won't Have (this phase) | Barcode/RFID/QR scanning (change candidate RFD-544); AI-based condition detection; native mobile app; multi-campus support; direct Sirius/clearance integration; multi-level approval (change candidate RFD-543) |

### 3.9.3 Requirements Traceability Matrix

| Req ID | Requirement | MoSCoW | Design basis | Build (Story/Task and Subtasks) | Verification (Task and Subtasks) |
| --- | --- | --- | --- | --- | --- |
| REQ-01 | Users sign in and are limited to the permissions of their role (borrower, custodian, administrator, auditor) | Must | RFD-484 (RFD-609, 611) | RFD-488 (RFD-619, 620, 621) | RFD-489 (RFD-622, 623); RFD-511 (RFD-677) |
| REQ-02 | Custodian and administrator maintain asset types, categories and individual asset units, with condition, status and archive rules | Must | RFD-482 (RFD-604–608) | RFD-490 (RFD-624, 625, 626) | RFD-491 (RFD-627, 628) |
| REQ-03 | Borrower browses and searches available assets and sees availability and borrowing requirements | Should | RFD-478 (RFD-594) | RFD-492 (RFD-629, 630, 631) | RFD-493 (RFD-632, 633) |
| REQ-04 | System evaluates borrower eligibility by role, program, status and asset, and shows the decision reason | Must | RFD-484 (RFD-610) | RFD-494 (RFD-634, 635, 636) | RFD-495 (RFD-637, 638) |
| REQ-05 | Borrower creates a borrowing ticket with validated asset, dates and quantity and receives a unique ticket number | Must | RFD-474 (RFD-584–586) | RFD-496 (RFD-639, 640, 641) | RFD-497 (RFD-643) |
| REQ-06 | Borrower tracks tickets and ticket details (My Requests) | Should | RFD-478 (RFD-594) | RFD-497 (RFD-642) | RFD-497 (RFD-643) |
| REQ-07 | Custodian approves or rejects a ticket; only authorized roles may decide | Must | RFD-474 (RFD-586) | RFD-474 (RFD-586) | RFD-501 (RFD-652) |
| REQ-08 | Student uses an AI chatbot for self-service; unanswered queries escalate to a ticket routed to the right department | Could | RFD-474 (RFD-585) | RFD-498 (RFD-644, 645, 646) | RFD-499 (RFD-647, 648) |
| REQ-09 | Custodian releases an approved asset after inspection checklist and borrower acknowledgment | Must | RFD-474 (RFD-584) | RFD-500 (RFD-649, 650, 651) | RFD-501 (RFD-652, 653) |
| REQ-10 | Custodian records return inspection and condition; damaged, lost or incomplete returns follow separate paths | Must | RFD-474 (RFD-585) | RFD-502 (RFD-654, 655, 656) | RFD-503 (RFD-658) |
| REQ-11 | Availability updates automatically and exactly once on release and on acceptable return | Must | RFD-482 (RFD-607) | RFD-500 (RFD-651); RFD-502 (RFD-655) | RFD-501 (RFD-653); RFD-503 (RFD-658) |
| REQ-12 | Completed tickets are closed and reconciled against transactions and inventory | Must | RFD-474 (RFD-586) | RFD-503 (RFD-657) | RFD-503 (RFD-658); RFD-508 (RFD-670) |
| REQ-13 | System detects overdue borrowing and generates daily reminders with history and a custodian overdue queue | Should | RFD-474 (RFD-585) | RFD-504 (RFD-659, 660, 661) | RFD-505 (RFD-663) |
| REQ-14 | Overdue cases can be sent as a controlled clearance referral or export (no live APC integration) | Should | RFD-485 (RFD-612, 613) | RFD-505 (RFD-662) | RFD-505 (RFD-663) |
| REQ-15 | Management monitors borrowing performance through approved KPIs, dashboards, filters and exports | Could | RFD-476 (RFD-590) | RFD-506 (RFD-664, 665, 666) | RFD-507 (RFD-668) |
| REQ-16 | Critical transactions are recorded in a role-restricted audit trail with administration controls | Should | RFD-484 (RFD-609) | RFD-507 (RFD-667) | RFD-507 (RFD-668) |
| REQ-NFR-01 | Security and privacy: access control, input validation, session security, no real personal data, secrets not exposed | Must | RFD-484 (RFD-611); RFD-486 (RFD-614) | RFD-486 (RFD-614, 615); RFD-487 (RFD-617) | RFD-511 (RFD-677, 678) |
| REQ-NFR-02 | Responsive, usable interface on supported browsers and mobile viewports | Should | RFD-478 (RFD-594, 595) | RFD-492 (RFD-629) | RFD-493 (RFD-633); RFD-509 (RFD-672) |
| REQ-NFR-03 | Data integrity: schema constraints, uniqueness and normalized relationships | Must | RFD-482 (RFD-605, 606, 607) | RFD-483 (RFD-608) | RFD-509 (RFD-672) |
| REQ-NFR-04 | Deployable and maintainable: production-like environment, migrations, documentation and archived evidence | Must | RFD-480 (RFD-599–603) | RFD-512 (RFD-679, 680) | RFD-512 (RFD-681); RFD-513 (RFD-682, 683) |

Jira keys are the live RFD backlog references (Epics RFD-463 to RFD-471). Subtask keys are shown in brackets after their parent Story or Task (RFD-579 to RFD-683; parentage inferred from export order and confirmed in Appendix D). REQ numbering follows the borrowing workflow order; the former REQ-01 to REQ-11 (keyed to RU-11 to RU-21) are retired and mapped in Appendix D.2.

Risk, defect and change coverage per requirement:

| Req ID | Linked Risks | Linked Defects (Bugs) | Linked Change Candidates |
| --- | --- | --- | --- |
| REQ-01 | RFD-520, RFD-523 | RFD-551, RFD-552, RFD-569, RFD-572 | RFD-542 |
| REQ-02 | — | RFD-550, RFD-553 | RFD-540 |
| REQ-03 | — | RFD-553, RFD-555 | — |
| REQ-04 | RFD-515, RFD-521 | RFD-554, RFD-556 | RFD-542 |
| REQ-05 | RFD-524 | RFD-548, RFD-556, RFD-557, RFD-559 | — |
| REQ-06 | — | RFD-559 | — |
| REQ-07 | RFD-525 | RFD-548, RFD-558 | RFD-543 |
| REQ-08 | — | — | — |
| REQ-09 | RFD-527 | RFD-560 | RFD-544 |
| REQ-10 | RFD-528 | RFD-562, RFD-563 | RFD-544 |
| REQ-11 | RFD-522, RFD-526 | RFD-560, RFD-561 | — |
| REQ-12 | RFD-526 | RFD-566, RFD-571, RFD-575 | — |
| REQ-13 | RFD-529, RFD-530 | RFD-564, RFD-565, RFD-566 | RFD-545 |
| REQ-14 | RFD-518, RFD-531 | RFD-567 | — |
| REQ-15 | RFD-532 | RFD-568, RFD-569 | RFD-546 |
| REQ-16 | RFD-533 | RFD-570 | — |
| REQ-NFR-01 | RFD-520, RFD-521, RFD-533, RFD-536 | RFD-551, RFD-572, RFD-573 | — |
| REQ-NFR-02 | — | RFD-549, RFD-574 | — |
| REQ-NFR-03 | RFD-522 | RFD-550 | — |
| REQ-NFR-04 | RFD-517, RFD-519, RFD-537, RFD-538, RFD-539 | RFD-576, RFD-577, RFD-578 | RFD-541 |

## 3.10 Risk Register

| Jira ID | Risk | Category | P | I | Score | Response (linked Jira items) |
| --- | --- | --- | --- | --- | --- | --- |
| RFD-514 E2 | Requirements rely on assumed rather than validated APC procedures | Stakeholder | 3 | 4 | 12-High | Validate procedures through documented stakeholder consultation (RFD-580); record assumptions; baseline approval review (RFD-593). |
| RFD-515 E4 | Eligibility rules vary across asset types or departments | Scope | 3 | 4 | 12-High | Configurable eligibility-rule records (RFD-634); per-role/program/asset test cases (RFD-637); PO confirms rule matrix with ITRO. |
| RFD-516 E2 | Prototype respondents do not represent actual custodians | Stakeholder | 3 | 3 | 9-Med | Include actual custodians/ITRO staff in prototype evaluation (RFD-597); analyze feedback by respondent role (RFD-598). |
| RFD-517 E3 | APC ITRO does not approve the proposed architecture | External/Academic | 2 | 4 | 8-Med | Present ADR with approval status and open questions (RFD-603); review early with ITRO; alternatives per Change RFD-541. |
| RFD-518 E3 | APC APIs or test environments are unavailable | External/Academic | 4 | 3 | 12-High | Design manual or mock fallback and controlled export (RFD-613); document integration points as proposed only (RFD-612). |
| RFD-519 E3 | Hosting cost exceeds the infrastructure baseline | Financial | 2 | 3 | 6-Med | Compare hosting options and cost (RFD-600); monitor billing against the ₱5,797.35 infrastructure baseline; fund from contingency reserve. |
| RFD-520 E3 | Repository or environment credentials are exposed | Data Privacy & Security | 2 | 5 | 10-Med | Secure repository (RFD-614); keep secrets out of code, documented configuration (RFD-617/618); rotate on exposure; see Bug RFD-551. |
| RFD-521 E4 | Incorrect eligibility rules approve unauthorized borrowers | Data Privacy & Security | 3 | 5 | 15-High | Rule test cases (RFD-637); bypass prevention and decision logging (RFD-638); PO sign-off of rule matrix before release. |
| RFD-522 E6 | Inventory availability becomes stale during concurrent requests | Technical | 3 | 4 | 12-High | Atomic availability updates in custody transaction (RFD-651); reconciliation (RFD-653, RFD-658). |
| RFD-523 E3 | Authentication design does not support future APC SSO | Technical | 2 | 3 | 6-Med | Map APC identity attributes (RFD-610); keep identity layer replaceable; integration specifications (RFD-485). |
| RFD-524 E5 | Users submit duplicate or conflicting reservations | Technical | 3 | 3 | 9-Med | Server-side validation of asset, dates and quantity (RFD-640); duplicate/invalid request tests (RFD-643). |
| RFD-525 E5 | A request is approved after inventory becomes unavailable | Technical | 3 | 4 | 12-High | Re-check availability at approval and release (RFD-651); unavailable-case tests (RFD-652). |
| RFD-526 E6 | Inventory is deducted or restored more than once | Technical | 3 | 4 | 12-High | Single-fire transactions and closure rules (RFD-651, RFD-657); reconciliation tests (RFD-658). |
| RFD-527 E6 | Asset-condition disputes occur without acknowledgment evidence | Operational | 3 | 3 | 9-Med | Preparation/inspection checklist (RFD-649); borrower acknowledgment at release (RFD-650); return inspection (RFD-654). |
| RFD-528 E6 | Damaged or lost assets return to availability incorrectly | Technical | 2 | 4 | 8-Med | Damaged/lost/incomplete-return paths (RFD-656); restore availability only for acceptable returns (RFD-655). |
| RFD-529 E7 | Notification service is unavailable or blocked | External/Academic | 3 | 3 | 9-Med | Reminder history and custodian overdue queue (RFD-660, RFD-661) as fallback; failure tests (RFD-663); channels per Change RFD-545. |
| RFD-530 E7 | Incorrect system time or dates create false overdue cases | Technical | 2 | 4 | 8-Med | Server-side date calculation and fixed time zone (RFD-659); date-edge and failure tests (RFD-663). |
| RFD-531 E7 | Clearance referral is mistaken for direct APC integration | Scope | 3 | 3 | 9-Med | Label output as controlled referral/export (RFD-662); document as proposed integration only (RFD-612/613); keep in exclusions. |
| RFD-532 E8 | Reports use incomplete or inaccurate data | Quality | 3 | 4 | 12-High | Approved KPI and calculation rules (RFD-664); calculation tests against source records (RFD-668). |
| RFD-533 E8 | Audit logs expose sensitive information to unauthorized roles | Data Privacy & Security | 2 | 4 | 8-Med | Role-restricted audit access (RFD-609/611); audit access tests (RFD-668); privacy verification (RFD-678). |
| RFD-534 E9 | Critical defects remain near the final deadline | Schedule | 3 | 5 | 15-High | Record defects and retest weekly (RFD-673); defect freeze before UAT; triage by Section 3.5.5 severity. |
| RFD-535 E9 | Insufficient UAT participants weaken acceptance evidence | Stakeholder | 3 | 4 | 12-High | Plan participants per role early (RFD-674); minimum borrower/custodian/administrator coverage; record limitations in evidence. |
| RFD-536 E9 | Test data contains real personal information | Data Privacy & Security | 1 | 5 | 5-Med | Synthetic seed data only (RFD-608, RFD-628); privacy verification before release (RFD-678). |
| RFD-537 E10 | Deployment environment differs from development | Technical | 3 | 3 | 9-Med | Production-like environment and checklist (RFD-679); smoke testing (RFD-680); Bugs RFD-576 to RFD-578. |
| RFD-538 E10 | Turnover lacks required documentation or access procedures | External/Academic | 2 | 3 | 6-Med | Finalize manuals (RFD-682); archive code, migrations and evidence (RFD-683); Transition Out Plan (Section 8.1). |
| RFD-539 E10 | Final stakeholder acceptance is delayed | Stakeholder | 3 | 4 | 12-High | Schedule demonstration early (RFD-681); collect sign-off evidence (RFD-676); escalate delay to Sponsor per Section 3.8.5. |

## 3.11 Configuration Management Plan

### 3.11.1 Configuration Management Approach

All project artifacts — source code, database schema, documentation, and Jira configuration — are version-controlled and treated as Configuration Items (CIs). GitHub is authoritative for code and schema scripts; Jira is authoritative for backlog/requirements state; this documentation set is authoritative for baselined plans.

### 3.11.2 Configuration Item Control

| Configuration Item | Version Control | Audit |
| --- | --- | --- |
| Source code (PHP application) | GitHub, feature-branch + PR review | Reviewed before every merge |
| Database schema | GitHub (schema scripts, migrations) | Validated before sprint design lock |
| Project documentation | Versioned document (v1.0, v2.0, v3.0…) | Reviewed at each planning gate |
| Jira backlog / configuration | Jira change history | Reviewed at sprint review |

## 3.12 Change Management Plan

### 3.12.1 Change Management Approach

Any change to Scope, Schedule, or Cost baselines is logged as a Jira Change issue (project RFD, e.g. RFD-540 to RFD-547), impact-assessed by the PM, and decided by the CCB before baselines are updated. Any approved change that adds scope or effort beyond the baseline will require additional fees. The cost is estimated at the member rates in Section 3.6.3 plus any added infrastructure cost, and it must be funded from the reserves or by additional Sponsor-approved budget before the change is implemented.

### 3.12.2 Change Control Board (CCB)

Hazel Gamalo (PM), Sheanne Guantero (PO), Carl Dominique Bueno (Adviser). Major scope changes also require Sponsor (Jojo Castillo) approval.

### 3.12.3 Change Classification Tiers

| Tier | Definition | Approval |
| --- | --- | --- |
| Minor | No impact on scope baseline, schedule, or cost | PM |
| Major | Affects one baseline (scope, schedule, or cost) but not multiple | CCB |
| Critical | Affects multiple baselines or threatens final submission | CCB + Sponsor |

### 3.12.4 Change Control Process

- 1. Submit Request — any stakeholder submits a CR as a Jira Change issue

- 2. Log — PM logs the CR in the Change Log with a unique CR ID

- 3. Impact Assessment — PM and team assess impact on Scope, Schedule, Cost, Quality, and Risk

- 4. CCB Review — CCB decides: Approve, Reject, or Defer

- 5. Implementation — if approved, baselines are updated and work is executed

- 6. Verification — the change is verified against its stated impact and closed

### 3.12.5 Change Log

| CR ID | Date | Description | Requested By | Tier / Status |
| --- | --- | --- | --- | --- |
| CR-01 | Aug 28, 2026 | Rescoped and renamed the project from the original proposal, "CampusFlow: AI Campus Service Hub" (a broad, AI-driven multi-department ticketing platform for IT support, registrar, guidance, and facilities, on Next.js/FastAPI/PostgreSQL+PGVector with OpenAI/Anthropic APIs), to "RAMS Flex: ITRO Equipment Borrowing and Return Tracking Prototype" — a single, well-defined workflow (equipment borrowing/return for ITRO) on PHP/MySQL/Apache/AWS Lightsail, with no AI chatbot component. Rationale: the original multi-department, AI-driven scope was not achievable to a testable, complete standard by a 5-person student team within a fixed 6-week schedule; narrowing to one workflow allows full completion, testing, and documentation. | Hazel Gamalo (PM), on behalf of Team TriTechPlus | Critical (multi-baseline) — Approved |
| CR-02 | Oct 9, 2026 | Re-baselined the Jira backlog from 3 epics / 22 stories (RU-1 to RU-26) to Jira project RFD: 9 epics, 21 stories, 21 tasks, 105 subtasks, plus Risk, Change and Bug issues (RFD-463 to RFD-683). Scope deltas versus the prior baseline: (a) limited AI chatbot for self-service and ticket escalation (RFD-498/499), which reverses the “no AI chatbot” position of CR-01; (b) eligibility evaluation and four roles including auditor; (c) overdue management, clearance referral/export, KPI reporting and audit trail; (d) two-step instructor + ITRO approval replaced by eligibility-driven custodian approval, with multi-level approval kept as change candidate RFD-543; (e) role and identity mapping designed for future APC SSO. WBS, RTM, risk register, sprint plans and schedule were re-keyed, and the plan was re-cut into 12 short sprints with role-based hours (Section 4); hour estimates, owners and sprint assignments need re-confirmation in Jira. | Project team (PM to confirm) | Critical (multi-baseline) — Proposed; pending CCB and Sponsor decision |
| RFD-540 | — (candidate) | Add or remove an asset category after stakeholder validation. Pre-registered change candidate (E4); impacts: Scope. Not yet submitted to the CCB. | — | Major (proposed tier) — Candidate, not submitted |
| RFD-541 | — (candidate) | Replace AWS Lightsail with another approved hosting environment. Pre-registered change candidate (E3); impacts: Cost, Schedule. Not yet submitted to the CCB. | — | Critical (proposed tier) — Candidate, not submitted |
| RFD-542 | — (candidate) | Add a new borrower role or eligibility rule. Pre-registered change candidate (E4); impacts: Scope. Not yet submitted to the CCB. | — | Major (proposed tier) — Candidate, not submitted |
| RFD-543 | — (candidate) | Add multi-level approval for selected asset categories. Pre-registered change candidate (E5); impacts: Scope, Schedule. Not yet submitted to the CCB. | — | Critical (proposed tier) — Candidate, not submitted |
| RFD-544 | — (candidate) | Add QR or barcode scanning to release and return. Pre-registered change candidate (E6); impacts: Scope, Schedule. Not yet submitted to the CCB. | — | Critical (proposed tier) — Candidate, not submitted |
| RFD-545 | — (candidate) | Add an approved email, SMS, or Teams notification channel. Pre-registered change candidate (E7); impacts: Scope. Not yet submitted to the CCB. | — | Major (proposed tier) — Candidate, not submitted |
| RFD-546 | — (candidate) | Add a new KPI or report requested by APC stakeholders. Pre-registered change candidate (E8); impacts: Scope. Not yet submitted to the CCB. | — | Major (proposed tier) — Candidate, not submitted |
| RFD-547 | — (candidate) | Revise acceptance criteria following approved UAT findings. Pre-registered change candidate (E9); impacts: Scope. Not yet submitted to the CCB. | — | Major (proposed tier) — Candidate, not submitted |

Approved by: Change Control Board (Hazel Gamalo – PM, Sheanne Guantero – PO, Carl Dominique Bueno – Adviser) and Project Sponsor (Jojo Castillo), per the Critical-tier approval path in Section 3.12.3. CR-02 and the RFD-540 to RFD-547 candidates have not yet been decided; they follow the same path (Sections 3.12.3–3.12.4).

# 4. Execution

The confirmed DEV baseline is 588 subtask hours across 21 tasks and 105 subtasks. Task story points total 147 and are tracked independently of labor hours. Member allocations are Hazel 116 h, July 116 h, Lancine 120 h, Patricia 120 h and Sheanne 116 h. The sprint grouping below is retained as a planning structure; dated commitments and item-level effort distribution require alignment with the current Jira calendar. The previous 300-hour proportional sprint allocation is withdrawn.

Sprint planning register — grouping retained; individual sprint hours require reconciliation

| Sprint | Dates | WPs | Sub-tasks | Hrs | Hazel | Lancine | July | Patricia | Sheanne |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| S1 | Aug 28 – Sep 1 | 3 | 8 | TBC | TBC | TBC | TBC | TBC | TBC |
| S2 | Sep 1 – Sep 4 | 4 | 10 | TBC | TBC | TBC | TBC | TBC | TBC |
| S3 | Sep 4 – Sep 8 | 3 | 7 | TBC | TBC | TBC | TBC | TBC | TBC |
| S4 | Sep 8 – Sep 11 | 4 | 10 | TBC | TBC | TBC | TBC | TBC | TBC |
| S5 | Sep 11 – Sep 15 | 3 | 8 | TBC | TBC | TBC | TBC | TBC | TBC |
| S6 | Sep 15 – Sep 18 | 4 | 10 | TBC | TBC | TBC | TBC | TBC | TBC |
| S7 | Sep 18 – Sep 22 | 3 | 7 | TBC | TBC | TBC | TBC | TBC | TBC |
| S8 | Sep 22 – Sep 25 | 4 | 10 | TBC | TBC | TBC | TBC | TBC | TBC |
| S9 | Sep 25 – Sep 29 | 3 | 8 | TBC | TBC | TBC | TBC | TBC | TBC |
| S10 | Sep 29 – Oct 2 | 4 | 10 | TBC | TBC | TBC | TBC | TBC | TBC |
| S11 | Oct 2 – Oct 6 | 3 | 7 | TBC | TBC | TBC | TBC | TBC | TBC |
| S12 | Oct 6 – Oct 9 | 4 | 10 | TBC | TBC | TBC | TBC | TBC | TBC |
| Total | Calendar pending | 42 | 105 | 588 | 116 | 120 | 116 | 120 | 116 |

## 4.1 Sprint 1 (Aug 28 – Sep 1, 2026)

Sprint 1 | Aug 28 – Sep 1, 2026 | Goal: Document the current borrowing experience; Create the current-state process map; Define the future borrowing-ticket lifecycle

| Jira ID | WBS | Backlog Item (Epic E2) | Type | Owner (proposed) | Sub-tasks | Hrs |
| --- | --- | --- | --- | --- | --- | --- |
| RFD-472 | 2.1 | Document the current borrowing experience | Story | Hazel | 3 | TBC |
| RFD-473 | 2.2 | Create the current-state process map | Task | Hazel | 2 | TBC |
| RFD-474 | 2.3 | Define the future borrowing-ticket lifecycle | Story | Hazel / Sheanne | 3 | TBC |

Sprint effort allocation: pending item-level reconciliation to the confirmed 588-hour DEV baseline. Subtasks: RFD-579–581, RFD-582–583, RFD-584–586.

| Daily Standup (Did / Doing / Blockers) | Backlog Refinement | Sprint Review | Retrospective (Start / Stop / Continue) |
| --- | --- | --- | --- |

## 4.2 Sprint 2 (Sep 1 – Sep 4, 2026)

Sprint 2 | Sep 1 – Sep 4, 2026 | Goal: Produce future-state workflow artifacts; Approve the system requirements; Build the Requirements Traceability Matrix; Validate the role-based user experience

| Jira ID | WBS | Backlog Item (Epic E2) | Type | Owner (proposed) | Sub-tasks | Hrs |
| --- | --- | --- | --- | --- | --- | --- |
| RFD-475 | 2.4 | Produce future-state workflow artifacts | Task | Hazel / Sheanne | 2 | TBC |
| RFD-476 | 2.5 | Approve the system requirements | Story | Sheanne / Hazel | 3 | TBC |
| RFD-477 | 2.6 | Build the Requirements Traceability Matrix | Task | Sheanne / Hazel | 2 | TBC |
| RFD-478 | 2.7 | Validate the role-based user experience | Story | July | 3 | TBC |

Sprint effort allocation: pending item-level reconciliation to the confirmed 588-hour DEV baseline. Subtasks: RFD-587–588, RFD-589–591, RFD-592–593, RFD-594–596.

| Daily Standup (Did / Doing / Blockers) | Backlog Refinement | Sprint Review | Retrospective (Start / Stop / Continue) |
| --- | --- | --- | --- |

## 4.3 Sprint 3 (Sep 4 – Sep 8, 2026)

Sprint 3 | Sep 4 – Sep 8, 2026 | Goal: Conduct prototype evaluation; Select an appropriate hosting architecture; Create Architecture Decision Record

| Jira ID | WBS | Backlog Item (Epic E2/E3) | Type | Owner (proposed) | Sub-tasks | Hrs |
| --- | --- | --- | --- | --- | --- | --- |
| RFD-479 | 2.8 | Conduct prototype evaluation | Task | July / Sheanne | 2 | TBC |
| RFD-480 | 3.1 | Select an appropriate hosting architecture | Story | Lancine | 3 | TBC |
| RFD-481 | 3.2 | Create Architecture Decision Record | Task | Lancine / Hazel | 2 | TBC |

Sprint effort allocation: pending item-level reconciliation to the confirmed 588-hour DEV baseline. Subtasks: RFD-597–598, RFD-599–601, RFD-602–603.

| Daily Standup (Did / Doing / Blockers) | Backlog Refinement | Sprint Review | Retrospective (Start / Stop / Continue) |
| --- | --- | --- | --- |

## 4.4 Sprint 4 (Sep 8 – Sep 11, 2026)

Sprint 4 | Sep 8 – Sep 11, 2026 | Goal: Establish the RAMS Flex data model; Produce database specifications; Define secure role and identity mapping; Prepare integration specifications

| Jira ID | WBS | Backlog Item (Epic E3) | Type | Owner (proposed) | Sub-tasks | Hrs |
| --- | --- | --- | --- | --- | --- | --- |
| RFD-482 | 3.3 | Establish the RAMS Flex data model | Story | Patricia | 3 | TBC |
| RFD-483 | 3.4 | Produce database specifications | Task | Patricia | 2 | TBC |
| RFD-484 | 3.5 | Define secure role and identity mapping | Story | Lancine | 3 | TBC |
| RFD-485 | 3.6 | Prepare integration specifications | Task | Patricia / Lancine | 2 | TBC |

Sprint effort allocation: pending item-level reconciliation to the confirmed 588-hour DEV baseline. Subtasks: RFD-604–606, RFD-607–608, RFD-609–611, RFD-612–613.

| Daily Standup (Did / Doing / Blockers) | Backlog Refinement | Sprint Review | Retrospective (Start / Stop / Continue) |
| --- | --- | --- | --- |

## 4.5 Sprint 5 (Sep 11 – Sep 15, 2026)

Sprint 5 | Sep 11 – Sep 15, 2026 | Goal: Establish collaborative source control; Configure development and test environments; Authenticate users and enforce roles

| Jira ID | WBS | Backlog Item (Epic E3) | Type | Owner (proposed) | Sub-tasks | Hrs |
| --- | --- | --- | --- | --- | --- | --- |
| RFD-486 | 3.7 | Establish collaborative source control | Story | Hazel | 3 | TBC |
| RFD-487 | 3.8 | Configure development and test environments | Task | Patricia / Lancine | 2 | TBC |
| RFD-488 | 3.9 | Authenticate users and enforce roles | Story | Lancine | 3 | TBC |

Sprint effort allocation: pending item-level reconciliation to the confirmed 588-hour DEV baseline. Subtasks: RFD-614–616, RFD-617–618, RFD-619–621.

| Daily Standup (Did / Doing / Blockers) | Backlog Refinement | Sprint Review | Retrospective (Start / Stop / Continue) |
| --- | --- | --- | --- |

## 4.6 Sprint 6 (Sep 15 – Sep 18, 2026)

Sprint 6 | Sep 15 – Sep 18, 2026 | Goal: Test authentication and authorization; Maintain asset records; Validate asset data; Browse and search available assets

| Jira ID | WBS | Backlog Item (Epic E3/E4) | Type | Owner (proposed) | Sub-tasks | Hrs |
| --- | --- | --- | --- | --- | --- | --- |
| RFD-489 | 3.10 | Test authentication and authorization | Task | Sheanne | 2 | TBC |
| RFD-490 | 4.1 | Maintain asset records | Story | Patricia | 3 | TBC |
| RFD-491 | 4.2 | Validate asset data | Task | Patricia / July | 2 | TBC |
| RFD-492 | 4.3 | Browse and search available assets | Story | July | 3 | TBC |

Sprint effort allocation: pending item-level reconciliation to the confirmed 588-hour DEV baseline. Subtasks: RFD-622–623, RFD-624–626, RFD-627–628, RFD-629–631.

| Daily Standup (Did / Doing / Blockers) | Backlog Refinement | Sprint Review | Retrospective (Start / Stop / Continue) |
| --- | --- | --- | --- |

## 4.7 Sprint 7 (Sep 18 – Sep 22, 2026)

Sprint 7 | Sep 18 – Sep 22, 2026 | Goal: Verify catalog accuracy and usability; Evaluate borrower eligibility; Test eligibility scenarios

| Jira ID | WBS | Backlog Item (Epic E4) | Type | Owner (proposed) | Sub-tasks | Hrs |
| --- | --- | --- | --- | --- | --- | --- |
| RFD-493 | 4.4 | Verify catalog accuracy and usability | Task | Sheanne | 2 | TBC |
| RFD-494 | 4.5 | Evaluate borrower eligibility | Story | Patricia | 3 | TBC |
| RFD-495 | 4.6 | Test eligibility scenarios | Task | Sheanne | 2 | TBC |

Sprint effort allocation: pending item-level reconciliation to the confirmed 588-hour DEV baseline. Subtasks: RFD-632–633, RFD-634–636, RFD-637–638.

| Daily Standup (Did / Doing / Blockers) | Backlog Refinement | Sprint Review | Retrospective (Start / Stop / Continue) |
| --- | --- | --- | --- |

## 4.8 Sprint 8 (Sep 22 – Sep 25, 2026)

Sprint 8 | Sep 22 – Sep 25, 2026 | Goal: Create a borrowing ticket; Implement borrower ticket tracking; Use an AI chatbot for self-service support and ticket escalation; Implement chatbot escalation rules and safeguards

| Jira ID | WBS | Backlog Item (Epic E5) | Type | Owner (proposed) | Sub-tasks | Hrs |
| --- | --- | --- | --- | --- | --- | --- |
| RFD-496 | 5.1 | Create a borrowing ticket | Story | Lancine / July | 3 | TBC |
| RFD-497 | 5.2 | Implement borrower ticket tracking | Task | July | 2 | TBC |
| RFD-498 | 5.3 | Use an AI chatbot for self-service support and ticket escalation | Story | Lancine | 3 | TBC |
| RFD-499 | 5.4 | Implement chatbot escalation rules and safeguards | Task | July / Lancine | 2 | TBC |

Sprint effort allocation: pending item-level reconciliation to the confirmed 588-hour DEV baseline. Subtasks: RFD-639–641, RFD-642–643, RFD-644–646, RFD-647–648.

| Daily Standup (Did / Doing / Blockers) | Backlog Refinement | Sprint Review | Retrospective (Start / Stop / Continue) |
| --- | --- | --- | --- |

## 4.9 Sprint 9 (Sep 25 – Sep 29, 2026)

Sprint 9 | Sep 25 – Sep 29, 2026 | Goal: Release an approved asset; Test release controls; Process asset return

| Jira ID | WBS | Backlog Item (Epic E6) | Type | Owner (proposed) | Sub-tasks | Hrs |
| --- | --- | --- | --- | --- | --- | --- |
| RFD-500 | 6.1 | Release an approved asset | Story | Patricia | 3 | TBC |
| RFD-501 | 6.2 | Test release controls | Task | Sheanne | 2 | TBC |
| RFD-502 | 6.3 | Process asset return | Story | Patricia | 3 | TBC |

Sprint effort allocation: pending item-level reconciliation to the confirmed 588-hour DEV baseline. Subtasks: RFD-649–651, RFD-652–653, RFD-654–656.

| Daily Standup (Did / Doing / Blockers) | Backlog Refinement | Sprint Review | Retrospective (Start / Stop / Continue) |
| --- | --- | --- | --- |

## 4.10 Sprint 10 (Sep 29 – Oct 2, 2026)

Sprint 10 | Sep 29 – Oct 2, 2026 | Goal: Close and reconcile borrowing records; Monitor overdue borrowing; Implement clearance referral and export; Monitor asset-borrowing performance

| Jira ID | WBS | Backlog Item (Epic E6/E7/E8) | Type | Owner (proposed) | Sub-tasks | Hrs |
| --- | --- | --- | --- | --- | --- | --- |
| RFD-503 | 6.4 | Close and reconcile borrowing records | Task | Patricia / Lancine | 2 | TBC |
| RFD-504 | 7.1 | Monitor overdue borrowing | Story | Lancine | 3 | TBC |
| RFD-505 | 7.2 | Implement clearance referral and export | Task | Patricia / July | 2 | TBC |
| RFD-506 | 8.1 | Monitor asset-borrowing performance | Story | July | 3 | TBC |

Sprint effort allocation: pending item-level reconciliation to the confirmed 588-hour DEV baseline. Subtasks: RFD-657–658, RFD-659–661, RFD-662–663, RFD-664–666.

| Daily Standup (Did / Doing / Blockers) | Backlog Refinement | Sprint Review | Retrospective (Start / Stop / Continue) |
| --- | --- | --- | --- |

## 4.11 Sprint 11 (Oct 2 – Oct 6, 2026)

Sprint 11 | Oct 2 – Oct 6, 2026 | Goal: Implement audit records and administration controls; Verify end-to-end borrowing operations; Conduct integration and compatibility testing

| Jira ID | WBS | Backlog Item (Epic E8/E9) | Type | Owner (proposed) | Sub-tasks | Hrs |
| --- | --- | --- | --- | --- | --- | --- |
| RFD-507 | 8.2 | Implement audit records and administration controls | Task | Patricia / July | 2 | TBC |
| RFD-508 | 9.1 | Verify end-to-end borrowing operations | Story | Sheanne | 3 | TBC |
| RFD-509 | 9.2 | Conduct integration and compatibility testing | Task | Sheanne | 2 | TBC |

Sprint effort allocation: pending item-level reconciliation to the confirmed 588-hour DEV baseline. Subtasks: RFD-667–668, RFD-669–671, RFD-672–673.

| Daily Standup (Did / Doing / Blockers) | Backlog Refinement | Sprint Review | Retrospective (Start / Stop / Continue) |
| --- | --- | --- | --- |

## 4.12 Sprint 12 (Oct 6 – Oct 9, 2026)

Sprint 12 | Oct 6 – Oct 9, 2026 | Goal: Obtain user acceptance evidence; Complete security and privacy verification; Deploy and accept the RAMS Flex MVP; Complete technical handover and release documentation

| Jira ID | WBS | Backlog Item (Epic E9/E10) | Type | Owner (proposed) | Sub-tasks | Hrs |
| --- | --- | --- | --- | --- | --- | --- |
| RFD-510 | 9.3 | Obtain user acceptance evidence | Story | Sheanne / Hazel | 3 | TBC |
| RFD-511 | 9.4 | Complete security and privacy verification | Task | Lancine | 2 | TBC |
| RFD-512 | 10.1 | Deploy and accept the RAMS Flex MVP | Story | Lancine / Hazel | 3 | TBC |
| RFD-513 | 10.2 | Complete technical handover and release documentation | Task | Hazel / Patricia | 2 | TBC |

Sprint effort allocation: pending item-level reconciliation to the confirmed 588-hour DEV baseline. Subtasks: RFD-674–676, RFD-677–678, RFD-679–681, RFD-682–683.

| Daily Standup (Did / Doing / Blockers) | Backlog Refinement | Sprint Review | Retrospective (Start / Stop / Continue) |
| --- | --- | --- | --- |

# 5. Agile

## 5.1 Agile Team Charter

Team Name: Team TriTechPlus.

Purpose: Deliver the RAMS Flex prototype within the 6-week academic timeline using Scrum, Agile values, and the governance defined in the Charter and supporting management plans.

Working Agreement:

- Sprints are short 3–4 day cadences (Friday–Tuesday and Tuesday–Friday), 12 in total, aligned to the Schedule Management Plan’s 7 milestones.

- Daily standups: 15 minutes, MS Teams, fixed 3-question format.

- Definition of Done: code reviewed, tested, acceptance criteria met, PO sign-off given.

- All scope changes go through the Change Control Process (Section 3.12.4) — no informal scope changes mid-sprint.

- Sheanne Guantero (PO) has final say on backlog priority; Hazel Gamalo (Scrum Master) has final say on process/ceremony adherence.

## 5.2 Agile Team Values

- Transparency — sprint status, defects, and blockers are visible in Jira for the whole team and PO, not just verbally reported.

- Inspect and Adapt — retrospective action items are tracked and actually applied in the next sprint, not just discussed.

- Sustainable Pace — plan commitments against each member’s confirmed DEV allocation and available calendar; include documentation and meeting obligations when reviewing total capacity.

- Customer Collaboration — proactive ITRO stakeholder consultation over rigid adherence to an untested initial plan.

- Courage — raising ambiguities as a formal Change Request the moment they're identified.

# 6. Project Documents

## 6.1 System Design Document

Architecture: PHP/MySQL, Monolithic (single AWS Lightsail instance: Ubuntu + Apache + PHP + MySQL), per Section 3.2.3. Application modules follow the Jira epics: authentication and role access (RFD-488), eligibility service (RFD-494), ticket lifecycle (RFD-496), custody and inventory (RFD-500/502), overdue and reminders (RFD-504), chatbot with escalation (RFD-498), and reports and audit (RFD-506/507). Role-based access is modeled on LDAP directory concepts; APC SSO and Sirius/clearance integrations are documented only (RFD-484/485).

Figure 3. RAMS Flex System Architecture Diagram (Jira-aligned)

### Core Entities (proposed — confirm against actual schema)

| Entity | Key Fields (proposed) | Notes |
| --- | --- | --- |
| Users / Roles | user_id, name, role, program, status | Role = Borrower / Custodian / Administrator / Auditor; APC identity and eligibility attributes (RFD-484) |
| Asset Types / Categories | type_id, category, name, borrowing requirements | Weighted toward cameras/video, laptops, webcams, clickers (RFD-490) |
| Asset Units | unit_id, type_id, status, condition, archived | Individual units; archive rule hides unit from catalog (RFD-490, Bug RFD-553) |
| Eligibility Rules | rule_id, role, program, status, asset scope | Configurable; decisions logged with reason (RFD-494) |
| Tickets / Ticket Items | ticket_id, user_id, unit/type, qty, dates, status | Unique ticket number; lifecycle statuses and transition rules (RFD-496, RFD-586) |
| Custody Transactions | transaction_id, ticket_id, released_by, acknowledgment, released_at | Created at release; triggers availability update (RFD-500) |
| Return Inspections | return_id, transaction_id, condition, outcome | Acceptable / damaged / lost / incomplete paths (RFD-502) |
| Reminders | reminder_id, ticket_id, sent_on, channel | One per day per overdue ticket; history retained (RFD-504) |
| Audit Log | event_id, actor, action, entity, timestamp | Critical transactions; role-restricted access (RFD-507) |
| Chatbot Escalations | escalation_id, user_id, context, department, ticket_id | Created when a query is unanswered; routed by department (RFD-498) |

### Core Workflow Sequence (high level)

- 1. Borrower browses the catalog; the system evaluates eligibility and the borrower creates a ticket (asset, dates, quantity) with duplicate and invalid-request checks

- 2. Custodian approves or rejects the ticket; availability is re-checked at decision time

- 3. Custodian completes the preparation/inspection checklist; borrower acknowledges; release creates a custody transaction and updates availability

- 4. Borrower returns the asset; custodian records return inspection and condition; acceptable returns restore availability, damaged/lost/incomplete returns follow separate paths

- 5. System closes and reconciles the ticket; overdue tickets generate daily reminders, appear in the custodian overdue queue, and may be sent as a controlled clearance referral; the chatbot escalates unanswered questions at any step; audit records and reports cover the lifecycle

Tech Stack Summary:

| Layer | Technology |
| --- | --- |
| Hosting | AWS Lightsail — single instance, Monolithic LAMP |
| Web Server | Apache |
| Application | PHP |
| Database | MySQL |
| Authentication | LDAP-concept role-based access (simulated): borrower, custodian, administrator, auditor; designed for future APC SSO |
| Project Tracking | Jira (project RFD) |
| Version Control | GitHub |

# 7. Monitoring and Controlling

This section contains the performance tracking reports.

## 7.1 Development baseline status

| Indicator | Position | Next action |
| --- | --- | --- |
| Planned DEV effort | 588 hours | Align issue estimates with confirmed allocation |
| Planned DEV labor cost | PHP 264,575.80 | Use confirmed member rates |
| Task story points | 147 across 21 tasks | Keep separate from cost and earned value |
| PV / EV / AC | Not yet validated | Reconcile schedule, acceptance and worklogs |
| CPI / SPI | Not calculated | Calculate after valid inputs exist |

## 7.2 Documentation status

Reporting date: 10 October 2026. Native leaf-work hours are reported separately from acceptance and monetary EVM.

| Indicator | Position | Interpretation |
| --- | --- | --- |
| Planned DOCS effort | 141.75 hours | Leaf-work estimates; excludes parent overlap |
| Planned DOCS labor cost | PHP 64,549.12 | Confirmed rates applied to recorded assignments |
| Recorded leaf-work effort | 138.25 hours | Worklog total; not an acceptance measure |
| Documentation status | 107 issues marked Done | Evidence required before EV is credited |
| PV / EV / AC and indices | Pending verification | No savings or completion claim from effort alone |

## 7.3 Meeting effort and combined labor baseline

| Indicator | Position | Interpretation |
| --- | --- | --- |
| Planned meeting effort | 206.25 student-hours | 41.25 hours each for five students |
| Planned meeting labor cost | PHP 92,886.34 | Confirmed rates; excludes adviser and instructor |
| Recorded meeting effort | 123.77 hours | Validate attendance and member-level logs |
| Combined planned labor | 936 hours / PHP 422,011.26 | DEV + DOCS + meetings |
| Monetary EVM | Pending verification | Retired EVM values are not current performance |

# 8. Closing

## 8.1 Transition Out Plan

- Source code repository access transferred/archived per APC/ITRO instructions (RFD-683)

- User, administrator and technical manuals handed over in final form (RFD-682, RFD-513)

- No real credentials to transfer — prototype uses simulated accounts only; deployment and configuration access procedures are documented in the handover (RFD-513, Risk RFD-538)

- Recorded final demonstration and acceptance evidence retained as an academic record (RFD-681)

- Knowledge transfer session offered to ITRO if a future funded phase is considered

## 8.2 Project Acceptance

Acceptance sequence: UAT sign-off (PO + ITRO Stakeholder; RFD-510) → Instructor review of documentation → final Sponsor sign-off at the demonstration (RFD-512).

| Role | Name | Signature | Date |
| --- | --- | --- | --- |
| Product Owner (UAT) | Sheanne Jennica P. Guantero | _____________________ | _____________ |
| ITRO Stakeholder | Ms. Grace Ann P. Morte | _____________________ | _____________ |
| PROJMAN Instructor | Felino Calderon III | _____________________ | _____________ |
| Project Sponsor | Jojo Castillo | _____________________ | _____________ |

## 8.3 Post Project Review Template

| Dimension | Revised plan | Actual position | Review action |
| --- | --- | --- | --- |
| Scope | Confirmed DEV / DOCS / meeting effort categories | Acceptance evidence pending | Review deliverables independently of Done status |
| Effort | 588 + 141.75 + 206.25 = 936 h | Complete actual effort not verified | Reconcile worklogs and attendance |
| Labor cost | PHP 422,011.26 | Actual cost pending verification | Apply confirmed rates to verified member worklogs |
| Overall budget | PHP 491,979.90 | Includes retained infrastructure assumptions | Confirm infrastructure and formal baseline approval |

## 8.4 Lessons Learned

- What went well this sprint / project?

- What could have gone better?

- What will the team do differently next time?

# Appendices

## Appendix A: Methodology

RAMS Flex uses a predictive scope, schedule and cost baseline with iterative Scrum execution. The work register contains 9 DEV epics, 21 stories, 21 tasks and 105 subtasks. Confirmed effort is 588 DEV hours, 141.75 DOCS hours and 206.25 meeting student-hours. Sprint dates and work-package allocation must be aligned in Jira before performance reporting.

## Appendix B: Detailed Schedule

## Appendix C: Detailed Cost Estimates

Section 3.6.3 contains the revised DEV, DOCS and meeting labor estimates, retained infrastructure assumptions and recalculated reserves. Rates and DEV allocations were confirmed by the project owner on 10 October 2026.

## Appendix D: Jira Work Packages

Full backlog register, transcribed from the Jira export of project RFD (221 issues, RFD-463 to RFD-683: 9 Epics, 21 Stories, 21 Tasks, 105 Subtasks, 26 Risks, 8 Changes, 31 Bugs). Subtask parentage is inferred from export order (each Story has 3 Subtasks and its companion Task has 2, in sequence) and must be confirmed against the Jira Parent field.

| Jira ID | Type | Title | Epic / Parent | WBS |
| --- | --- | --- | --- | --- |
| RFD-463 | Epic | E2 - Requirements and Product Design | — | 2 |
| RFD-464 | Epic | E3 - Architecture and Engineering | — | 3 |
| RFD-465 | Epic | E4 - Asset Catalog and Eligibility | — | 4 |
| RFD-466 | Epic | E5 - Borrowing Ticket Lifecycle | — | 5 |
| RFD-467 | Epic | E6 - Inventory and Asset Custody | — | 6 |
| RFD-468 | Epic | E7 - Notifications and Overdue Management | — | 7 |
| RFD-469 | Epic | E8 - Administration, Audit and Reporting | — | 8 |
| RFD-470 | Epic | E9 - Quality Assurance and Verification | — | 9 |
| RFD-471 | Epic | E10 - Deployment, Handover and Closure | — | 10 |
| RFD-472 | Story | Document the current borrowing experience | RFD-463 | 2.1 |
| RFD-473 | Task | Create the current-state process map | RFD-463 | 2.2 |
| RFD-474 | Story | Define the future borrowing-ticket lifecycle | RFD-463 | 2.3 |
| RFD-475 | Task | Produce future-state workflow artifacts | RFD-463 | 2.4 |
| RFD-476 | Story | Approve the system requirements | RFD-463 | 2.5 |
| RFD-477 | Task | Build the Requirements Traceability Matrix | RFD-463 | 2.6 |
| RFD-478 | Story | Validate the role-based user experience | RFD-463 | 2.7 |
| RFD-479 | Task | Conduct prototype evaluation | RFD-463 | 2.8 |
| RFD-480 | Story | Select an appropriate hosting architecture | RFD-464 | 3.1 |
| RFD-481 | Task | Create Architecture Decision Record | RFD-464 | 3.2 |
| RFD-482 | Story | Establish the RAMS Flex data model | RFD-464 | 3.3 |
| RFD-483 | Task | Produce database specifications | RFD-464 | 3.4 |
| RFD-484 | Story | Define secure role and identity mapping | RFD-464 | 3.5 |
| RFD-485 | Task | Prepare integration specifications | RFD-464 | 3.6 |
| RFD-486 | Story | Establish collaborative source control | RFD-464 | 3.7 |
| RFD-487 | Task | Configure development and test environments | RFD-464 | 3.8 |
| RFD-488 | Story | Authenticate users and enforce roles | RFD-464 | 3.9 |
| RFD-489 | Task | Test authentication and authorization | RFD-464 | 3.10 |
| RFD-490 | Story | Maintain asset records | RFD-465 | 4.1 |
| RFD-491 | Task | Validate asset data | RFD-465 | 4.2 |
| RFD-492 | Story | Browse and search available assets | RFD-465 | 4.3 |
| RFD-493 | Task | Verify catalog accuracy and usability | RFD-465 | 4.4 |
| RFD-494 | Story | Evaluate borrower eligibility | RFD-465 | 4.5 |
| RFD-495 | Task | Test eligibility scenarios | RFD-465 | 4.6 |
| RFD-496 | Story | Create a borrowing ticket | RFD-466 | 5.1 |
| RFD-497 | Task | Implement borrower ticket tracking | RFD-466 | 5.2 |
| RFD-498 | Story | Use an AI chatbot for self-service support and ticket escalation | RFD-466 | 5.3 |
| RFD-499 | Task | Implement chatbot escalation rules and safeguards | RFD-466 | 5.4 |
| RFD-500 | Story | Release an approved asset | RFD-467 | 6.1 |
| RFD-501 | Task | Test release controls | RFD-467 | 6.2 |
| RFD-502 | Story | Process asset return | RFD-467 | 6.3 |
| RFD-503 | Task | Close and reconcile borrowing records | RFD-467 | 6.4 |
| RFD-504 | Story | Monitor overdue borrowing | RFD-468 | 7.1 |
| RFD-505 | Task | Implement clearance referral and export | RFD-468 | 7.2 |
| RFD-506 | Story | Monitor asset-borrowing performance | RFD-469 | 8.1 |
| RFD-507 | Task | Implement audit records and administration controls | RFD-469 | 8.2 |
| RFD-508 | Story | Verify end-to-end borrowing operations | RFD-470 | 9.1 |
| RFD-509 | Task | Conduct integration and compatibility testing | RFD-470 | 9.2 |
| RFD-510 | Story | Obtain user acceptance evidence | RFD-470 | 9.3 |
| RFD-511 | Task | Complete security and privacy verification | RFD-470 | 9.4 |
| RFD-512 | Story | Deploy and accept the RAMS Flex MVP | RFD-471 | 10.1 |
| RFD-513 | Task | Complete technical handover and release documentation | RFD-471 | 10.2 |
| RFD-514 | Risk | Requirements rely on assumed rather than validated APC procedures | RFD-463 | — |
| RFD-515 | Risk | Eligibility rules vary across asset types or departments | RFD-465 | — |
| RFD-516 | Risk | Prototype respondents do not represent actual custodians | RFD-463 | — |
| RFD-517 | Risk | APC ITRO does not approve the proposed architecture | RFD-464 | — |
| RFD-518 | Risk | APC APIs or test environments are unavailable | RFD-464 | — |
| RFD-519 | Risk | Hosting cost exceeds the infrastructure baseline | RFD-464 | — |
| RFD-520 | Risk | Repository or environment credentials are exposed | RFD-464 | — |
| RFD-521 | Risk | Incorrect eligibility rules approve unauthorized borrowers | RFD-465 | — |
| RFD-522 | Risk | Inventory availability becomes stale during concurrent requests | RFD-467 | — |
| RFD-523 | Risk | Authentication design does not support future APC SSO | RFD-464 | — |
| RFD-524 | Risk | Users submit duplicate or conflicting reservations | RFD-466 | — |
| RFD-525 | Risk | A request is approved after inventory becomes unavailable | RFD-466 | — |
| RFD-526 | Risk | Inventory is deducted or restored more than once | RFD-467 | — |
| RFD-527 | Risk | Asset-condition disputes occur without acknowledgment evidence | RFD-467 | — |
| RFD-528 | Risk | Damaged or lost assets return to availability incorrectly | RFD-467 | — |
| RFD-529 | Risk | Notification service is unavailable or blocked | RFD-468 | — |
| RFD-530 | Risk | Incorrect system time or dates create false overdue cases | RFD-468 | — |
| RFD-531 | Risk | Clearance referral is mistaken for direct APC integration | RFD-468 | — |
| RFD-532 | Risk | Reports use incomplete or inaccurate data | RFD-469 | — |
| RFD-533 | Risk | Audit logs expose sensitive information to unauthorized roles | RFD-469 | — |
| RFD-534 | Risk | Critical defects remain near the final deadline | RFD-470 | — |
| RFD-535 | Risk | Insufficient UAT participants weaken acceptance evidence | RFD-470 | — |
| RFD-536 | Risk | Test data contains real personal information | RFD-470 | — |
| RFD-537 | Risk | Deployment environment differs from development | RFD-471 | — |
| RFD-538 | Risk | Turnover lacks required documentation or access procedures | RFD-471 | — |
| RFD-539 | Risk | Final stakeholder acceptance is delayed | RFD-471 | — |
| RFD-540 | Change | Add or remove an asset category after stakeholder validation | RFD-465 | — |
| RFD-541 | Change | Replace AWS Lightsail with another approved hosting environment | RFD-464 | — |
| RFD-542 | Change | Add a new borrower role or eligibility rule | RFD-465 | — |
| RFD-543 | Change | Add multi-level approval for selected asset categories | RFD-466 | — |
| RFD-544 | Change | Add QR or barcode scanning to release and return | RFD-467 | — |
| RFD-545 | Change | Add an approved email, SMS, or Teams notification channel | RFD-468 | — |
| RFD-546 | Change | Add a new KPI or report requested by APC stakeholders | RFD-469 | — |
| RFD-547 | Change | Revise acceptance criteria following approved UAT findings | RFD-470 | — |
| RFD-548 | Bug | Prototype permits bypass of a required workflow step | RFD-463 | — |
| RFD-549 | Bug | Prototype navigation or labels conflict with approved terminology | RFD-463 | — |
| RFD-550 | Bug | Database constraint permits invalid borrowing data | RFD-464 | — |
| RFD-551 | Bug | Application configuration exposes secrets or environment details | RFD-464 | — |
| RFD-552 | Bug | User accesses a route outside the assigned role | RFD-464 | — |
| RFD-553 | Bug | Archived asset appears in the borrower catalog | RFD-465 | — |
| RFD-554 | Bug | Eligibility result conflicts with configured rule | RFD-465 | — |
| RFD-555 | Bug | Catalog quantity conflicts with inventory records | RFD-465 | — |
| RFD-556 | Bug | Ineligible user submits a borrowing ticket | RFD-466 | — |
| RFD-557 | Bug | Duplicate ticket number is generated | RFD-466 | — |
| RFD-558 | Bug | Unauthorized user approves or rejects a ticket | RFD-466 | — |
| RFD-559 | Bug | Ticket enters an invalid lifecycle status | RFD-466 | — |
| RFD-560 | Bug | Inventory is reduced before physical release | RFD-467 | — |
| RFD-561 | Bug | Available quantity becomes negative | RFD-467 | — |
| RFD-562 | Bug | Return restores the wrong asset unit or quantity | RFD-467 | — |
| RFD-563 | Bug | Lost or damaged asset appears available | RFD-467 | — |
| RFD-564 | Bug | Reminder is sent before the due date | RFD-468 | — |
| RFD-565 | Bug | Duplicate daily reminders are generated | RFD-468 | — |
| RFD-566 | Bug | Returned ticket remains overdue | RFD-468 | — |
| RFD-567 | Bug | Referral export exposes unnecessary personal information | RFD-468 | — |
| RFD-568 | Bug | Dashboard total conflicts with source records | RFD-469 | — |
| RFD-569 | Bug | Unauthorized role accesses management reports | RFD-469 | — |
| RFD-570 | Bug | Critical transaction is missing from the audit trail | RFD-469 | — |
| RFD-571 | Bug | Critical end-to-end borrowing scenario fails | RFD-470 | — |
| RFD-572 | Bug | Broken access control permits unauthorized action | RFD-470 | — |
| RFD-573 | Bug | Invalid input produces an unhandled server error | RFD-470 | — |
| RFD-574 | Bug | Layout is unusable on a supported mobile viewport | RFD-470 | — |
| RFD-575 | Bug | UAT action creates inconsistent ticket and inventory records | RFD-470 | — |
| RFD-576 | Bug | Deployed application cannot connect to the database | RFD-471 | — |
| RFD-577 | Bug | Environment configuration causes broken links or missing resources | RFD-471 | — |
| RFD-578 | Bug | Deployment package omits a required migration or configuration file | RFD-471 | — |
| RFD-579 | Subtask | Prepare interview and workflow-validation questions | RFD-472 | 2.1.1 |
| RFD-580 | Subtask | Conduct or document stakeholder consultation | RFD-472 | 2.1.2 |
| RFD-581 | Subtask | Analyze pain points, delays, and control gaps | RFD-472 | 2.1.3 |
| RFD-582 | Subtask | Model the current workflow and responsible actors | RFD-473 | 2.2.1 |
| RFD-583 | Subtask | Review and revise the process map | RFD-473 | 2.2.2 |
| RFD-584 | Subtask | Define main borrowing lifecycle and statuses | RFD-474 | 2.3.1 |
| RFD-585 | Subtask | Define exceptions and escalation paths | RFD-474 | 2.3.2 |
| RFD-586 | Subtask | Define status-transition rules | RFD-474 | 2.3.3 |
| RFD-587 | Subtask | Create future-state BPMN/process diagram | RFD-475 | 2.4.1 |
| RFD-588 | Subtask | Validate the future workflow with stakeholders | RFD-475 | 2.4.2 |
| RFD-589 | Subtask | Write functional requirements | RFD-476 | 2.5.1 |
| RFD-590 | Subtask | Write non-functional and data requirements | RFD-476 | 2.5.2 |
| RFD-591 | Subtask | Review and prioritize requirements | RFD-476 | 2.5.3 |
| RFD-592 | Subtask | Map requirements to epics, stories, designs, and tests | RFD-477 | 2.6.1 |
| RFD-593 | Subtask | Review gaps and obtain baseline approval | RFD-477 | 2.6.2 |
| RFD-594 | Subtask | Design borrower wireframes | RFD-478 | 2.7.1 |
| RFD-595 | Subtask | Design custodian and administrator wireframes | RFD-478 | 2.7.2 |
| RFD-596 | Subtask | Create clickable prototype | RFD-478 | 2.7.3 |
| RFD-597 | Subtask | Prepare and conduct prototype evaluation | RFD-479 | 2.8.1 |
| RFD-598 | Subtask | Analyze feedback and revise prototype | RFD-479 | 2.8.2 |
| RFD-599 | Subtask | Define application, database, storage, and network components | RFD-480 | 3.1.1 |
| RFD-600 | Subtask | Compare Lightsail, local hosting, and approved alternatives | RFD-480 | 3.1.2 |
| RFD-601 | Subtask | Document security, backup, and maintenance considerations | RFD-480 | 3.1.3 |
| RFD-602 | Subtask | Prepare logical and deployment diagrams | RFD-481 | 3.2.1 |
| RFD-603 | Subtask | Record decision, approval status, and open questions | RFD-481 | 3.2.2 |
| RFD-604 | Subtask | Identify entities, fields, and business rules | RFD-482 | 3.3.1 |
| RFD-605 | Subtask | Create conceptual and logical ERD | RFD-482 | 3.3.2 |
| RFD-606 | Subtask | Normalize and validate relationships | RFD-482 | 3.3.3 |
| RFD-607 | Subtask | Prepare data dictionary and constraints | RFD-483 | 3.4.1 |
| RFD-608 | Subtask | Create initial MySQL schema and seed-data plan | RFD-483 | 3.4.2 |
| RFD-609 | Subtask | Define borrower, custodian, administrator, and auditor permissions | RFD-484 | 3.5.1 |
| RFD-610 | Subtask | Define APC identity and eligibility attributes | RFD-484 | 3.5.2 |
| RFD-611 | Subtask | Define authorization and access-denial rules | RFD-484 | 3.5.3 |
| RFD-612 | Subtask | Document proposed Sirius and clearance integration points | RFD-485 | 3.6.1 |
| RFD-613 | Subtask | Design manual or mock fallback and controlled export | RFD-485 | 3.6.2 |
| RFD-614 | Subtask | Create and secure GitHub repository | RFD-486 | 3.7.1 |
| RFD-615 | Subtask | Define branch, commit, review, and merge conventions | RFD-486 | 3.7.2 |
| RFD-616 | Subtask | Connect commits and pull requests to Jira | RFD-486 | 3.7.3 |
| RFD-617 | Subtask | Configure PHP and MySQL application environment | RFD-487 | 3.8.1 |
| RFD-618 | Subtask | Create test database and configuration guide | RFD-487 | 3.8.2 |
| RFD-619 | Subtask | Develop login, logout, and session handling | RFD-488 | 3.9.1 |
| RFD-620 | Subtask | Implement user-role mapping | RFD-488 | 3.9.2 |
| RFD-621 | Subtask | Protect borrower, custodian, and administrator routes | RFD-488 | 3.9.3 |
| RFD-622 | Subtask | Create positive and negative RBAC tests | RFD-489 | 3.10.1 |
| RFD-623 | Subtask | Document access-control results | RFD-489 | 3.10.2 |
| RFD-624 | Subtask | Develop asset-type and category management | RFD-490 | 4.1.1 |
| RFD-625 | Subtask | Develop individual asset-unit management | RFD-490 | 4.1.2 |
| RFD-626 | Subtask | Implement condition, status, and archive rules | RFD-490 | 4.1.3 |
| RFD-627 | Subtask | Implement server-side validation and uniqueness rules | RFD-491 | 4.2.1 |
| RFD-628 | Subtask | Prepare initial asset test data | RFD-491 | 4.2.2 |
| RFD-629 | Subtask | Develop responsive catalog interface | RFD-492 | 4.3.1 |
| RFD-630 | Subtask | Implement search, filter, and pagination | RFD-492 | 4.3.2 |
| RFD-631 | Subtask | Display availability and borrowing requirements | RFD-492 | 4.3.3 |
| RFD-632 | Subtask | Test catalog results against database records | RFD-493 | 4.4.1 |
| RFD-633 | Subtask | Conduct responsive and usability checks | RFD-493 | 4.4.2 |
| RFD-634 | Subtask | Develop configurable eligibility-rule records | RFD-494 | 4.5.1 |
| RFD-635 | Subtask | Implement eligibility evaluation service | RFD-494 | 4.5.2 |
| RFD-636 | Subtask | Display eligibility result and decision reason | RFD-494 | 4.5.3 |
| RFD-637 | Subtask | Prepare role, program, status, and asset test cases | RFD-495 | 4.6.1 |
| RFD-638 | Subtask | Verify bypass prevention and decision logging | RFD-495 | 4.6.2 |
| RFD-639 | Subtask | Develop request cart interface | RFD-496 | 5.1.1 |
| RFD-640 | Subtask | Validate asset, dates, quantity, and eligibility | RFD-496 | 5.1.2 |
| RFD-641 | Subtask | Generate ticket number and submission record | RFD-496 | 5.1.3 |
| RFD-642 | Subtask | Develop My Requests and ticket-detail views | RFD-497 | 5.2.1 |
| RFD-643 | Subtask | Test duplicate and invalid request handling | RFD-497 | 5.2.2 |
| RFD-644 | Subtask | Develop the student chatbot conversation interface | RFD-498 | 5.3.1 |
| RFD-645 | Subtask | Detect unanswered queries and collect ticket context | RFD-498 | 5.3.2 |
| RFD-646 | Subtask | Create and route escalated tickets to the appropriate department | RFD-498 | 5.3.3 |
| RFD-647 | Subtask | Configure approved-source, confidence, and fallback rules | RFD-499 | 5.4.1 |
| RFD-648 | Subtask | Test escalation routing, privacy, and unauthorized access controls | RFD-499 | 5.4.2 |
| RFD-649 | Subtask | Develop preparation and inspection checklist | RFD-500 | 6.1.1 |
| RFD-650 | Subtask | Implement release and borrower acknowledgment | RFD-500 | 6.1.2 |
| RFD-651 | Subtask | Create custody transaction and update availability | RFD-500 | 6.1.3 |
| RFD-652 | Subtask | Test approved, rejected, and unavailable cases | RFD-501 | 6.2.1 |
| RFD-653 | Subtask | Reconcile ticket, transaction, and inventory data | RFD-501 | 6.2.2 |
| RFD-654 | Subtask | Develop return inspection and condition recording | RFD-502 | 6.3.1 |
| RFD-655 | Subtask | Restore availability for acceptable returns | RFD-502 | 6.3.2 |
| RFD-656 | Subtask | Create damaged, lost, or incomplete-return paths | RFD-502 | 6.3.3 |
| RFD-657 | Subtask | Implement closure rules and transaction history | RFD-503 | 6.4.1 |
| RFD-658 | Subtask | Test inventory reconciliation after return | RFD-503 | 6.4.2 |
| RFD-659 | Subtask | Implement due-date calculation and overdue detection | RFD-504 | 7.1.1 |
| RFD-660 | Subtask | Create daily reminder generation and history | RFD-504 | 7.1.2 |
| RFD-661 | Subtask | Develop custodian overdue queue | RFD-504 | 7.1.3 |
| RFD-662 | Subtask | Create controlled overdue referral or export | RFD-505 | 7.2.1 |
| RFD-663 | Subtask | Test escalation, acknowledgment, and reminder failures | RFD-505 | 7.2.2 |
| RFD-664 | Subtask | Define approved KPIs and calculation rules | RFD-506 | 8.1.1 |
| RFD-665 | Subtask | Develop dashboard queries and summaries | RFD-506 | 8.1.2 |
| RFD-666 | Subtask | Develop filters and report or export views | RFD-506 | 8.1.3 |
| RFD-667 | Subtask | Record critical transaction events | RFD-507 | 8.2.1 |
| RFD-668 | Subtask | Test audit search, access, and report calculations | RFD-507 | 8.2.2 |
| RFD-669 | Subtask | Execute authentication, catalog, and eligibility tests | RFD-508 | 9.1.1 |
| RFD-670 | Subtask | Execute request, approval, release, and return tests | RFD-508 | 9.1.2 |
| RFD-671 | Subtask | Execute overdue, reporting, and audit tests | RFD-508 | 9.1.3 |
| RFD-672 | Subtask | Test database integrity, responsiveness, and browser compatibility | RFD-509 | 9.2.1 |
| RFD-673 | Subtask | Record defects, retest fixes, and update RTM | RFD-509 | 9.2.2 |
| RFD-674 | Subtask | Prepare UAT plan, scripts, participants, and test data | RFD-510 | 9.3.1 |
| RFD-675 | Subtask | Conduct borrower, custodian, and administrator UAT | RFD-510 | 9.3.2 |
| RFD-676 | Subtask | Analyze results and obtain acceptance sign-off | RFD-510 | 9.3.3 |
| RFD-677 | Subtask | Test authentication, authorization, validation, and session controls | RFD-511 | 9.4.1 |
| RFD-678 | Subtask | Verify privacy controls and close release-blocking defects | RFD-511 | 9.4.2 |
| RFD-679 | Subtask | Prepare production-like environment and deployment checklist | RFD-512 | 10.1.1 |
| RFD-680 | Subtask | Deploy and conduct smoke testing | RFD-512 | 10.1.2 |
| RFD-681 | Subtask | Conduct final demonstration and obtain acceptance evidence | RFD-512 | 10.1.3 |
| RFD-682 | Subtask | Finalize user, administrator, and technical manuals | RFD-513 | 10.2.1 |
| RFD-683 | Subtask | Archive source code, migrations, test evidence, and deployment records | RFD-513 | 10.2.2 |

D.2 Crosswalk from the retired RU keys to the RFD keys:

| Retired Jira key | Replacement (RFD) | Note |
| --- | --- | --- |
| RU-1 (Epic) Foundation & Design | RFD-463 (E2), RFD-464 (E3) | Split into two epics |
| RU-2 (Epic) Workflow & Lifecycle | RFD-465 (E4), RFD-466 (E5), RFD-467 (E6) | Split into three epics |
| RU-3 (Epic) Testing, QA & Closure | RFD-470 (E9), RFD-471 (E10) | Split into two epics; E7, E8 are new |
| RU-4 Project Charter | No RFD item (Section 2.1) | Epic E1 not in export |
| RU-5 Stakeholder Management Strategy | No RFD item (Sections 2.4–2.5); consultation in RFD-580 | Epic E1 not in export |
| RU-6 Requirements, WBS, RACI & Jira Backlog Setup | RFD-476, RFD-477 | E2 |
| RU-7 Schedule & Budget Baseline | No RFD item (Sections 3.4, 3.6) | Epic E1 not in export |
| RU-8 Architecture Design | RFD-480, RFD-481 | E3 |
| RU-9 Database Schema Design | RFD-482, RFD-483 | E3 |
| RU-10 Wireframes / UI Design | RFD-478, RFD-479 | E2 |
| RU-11 Simulated Role-Based Sign-In | RFD-484, RFD-488, RFD-489 | E3 |
| RU-12 Browse the Equipment Catalogue | RFD-490–493 | E4 (asset records added) |
| RU-13 Submit a Borrowing Request | RFD-496, RFD-497 (with RFD-494/495 eligibility) | E4, E5 |
| RU-14 Instructor/Department Head Verification | RFD-494, RFD-495 (eligibility); multi-level approval = Change RFD-543 | Replaced, no direct equivalent |
| RU-15 ITRO Staff Approve or Decline | No dedicated item (partly RFD-652; Bug RFD-558) | GAP – see REQ-07 |
| RU-16 Track Request Status | RFD-497 (RFD-642) | E5 |
| RU-17 View Request History | RFD-497 (RFD-642); RFD-657 (transaction history) | E5, E6 |
| RU-18 Record Equipment Release with Condition Check | RFD-500, RFD-501 | E6 |
| RU-19 Record Equipment Return with Condition Check | RFD-502 | E6 |
| RU-20 Automatic Availability Update | RFD-500 (RFD-651), RFD-502 (RFD-655) | E6 |
| RU-21 Close a Completed Transaction | RFD-503 | E6 |
| RU-22 Functional, Integration & Role-Access Testing | RFD-508, RFD-509 | E9 |
| RU-23 Defect Resolution and Retesting | RFD-509 (RFD-673); Bugs RFD-548–578 | E9 |
| RU-24 UAT with ITRO | RFD-510 | E9 |
| RU-25 Documentation and Repository | RFD-513 (RFD-682, 683); RFD-486 | E10, E3 |
| RU-26 Final Demonstration and Academic Submission | RFD-512 (RFD-681) | E10 |

## Appendix E: Change Request Form

| Field | Detail |
| --- | --- |
| CR ID |  |
| Date Submitted |  |
| Requested By |  |
| Description |  |
| Impact (Scope/Schedule/Cost/Risk) |  |
| CCB Decision |  |

## Appendix F: Project Acceptance Form

| Field | Detail |
| --- | --- |
| Deliverable |  |
| Acceptance Criteria Met? (Y/N) |  |
| Reviewer |  |
| Date |  |
| Comments |  |

## Appendix G: Links

| Resource | Link |
| --- | --- |
| GitHub Repository | [insert link] |
| Jira Project (key RFD) | [insert link] |
| Cloud Drive (shared docs) | [insert link] |
| Sample Prototype (click-through) | [insert link] |

## Appendix H Review Findings Log updated 10 October 2026

| # | Section | Issue | Severity | Solution | Status |
| --- | --- | --- | --- | --- | --- |
| 1 | 3.6.4 | Schedule baseline remains inconsistent with current implementation planning | High | Publish one dated calendar and time-phase the revised work-package budgets | Open |
| 2 | 3.6.4 | Historical EVM results used the retired labor model | High | Withdrawn and replaced with correct formulas and reporting prerequisites | Corrected in document |
| 3 | 3.6.4, 7 | Actual labor cost and meeting attendance are not fully verified | High | Reconcile member worklogs and attendance before calculating AC or CPI | Open |
| 4 | 3.6.4, 7.1 | EV requires acceptance evidence and a non-overlapping cost basis | Medium | Use 0/100 accepted-deliverable rule; attach evidence before crediting EV | Open |
| 5 | 3.6.4, 8.3 | Labor BAC must be separated from infrastructure and reserves | Medium | Labor BAC PHP 422,011.26; total planned budget PHP 491,979.90 | Corrected in document |
| 6 | 4.6 | Retired 300-hour sprint allocation | Low | Replaced with 588-hour DEV baseline; item-level sprint distribution pending | Baseline corrected |
| 7 | 3.7.2 | RACI: two A’s in “UAT & Final Demonstration”; Sponsor is R on the Charter | Medium | One A per row (see Flag 7) | Open |
| 8 | 3.8.3, 3.10 | Score of 5 labelled Low but bands say 5–10 is Medium | Low | Relabelled to 5-Med | Fixed |
| 9 | 3.6.5 | No rule for implausibly good CPI/SPI | Low | Added “Anomaly” row (> 1.20 → audit data) | Fixed |
| 10 | 3.3, 3.9.3, App. D | Jira re-baseline: RU-1 to RU-26 replaced by RFD-463 to RFD-683; export has no Parent, Sprint, Owner, Estimate or Status fields | High | WBS, RTM, logs, sprint plans, schedule and Appendix D re-keyed; sprint allocation and owners are proposed; confirm in Jira and re-export with those fields | Open |
| 11 | 3.9.3 | REQ-07 (custodian approves/rejects a ticket) has no dedicated Jira Story, Task or Subtask | High | Add an approval/rejection Subtask under RFD-497 (or a new E5 Story); trace to RFD-558, RFD-525 | Open |
| 12 | 3.2, 3.12.5 | Chatbot (RFD-498/499), eligibility-driven approval and new roles change the approved scope; CR-01 had excluded an AI chatbot | High | CR-02 raised (Critical tier); CCB and Sponsor decision required before baseline update | Open |
| 13 | 3.3, App. D | Epic E1 not in the export; subtask parentage inferred from key order | Medium | Re-export including Parent; confirm or create E1 for initiation/planning documents | Open |
| 14 | 3.6.4, 7 | Jira estimates and PV/EV need alignment with confirmed DEV hours | Medium | Use 588 DEV hours and confirmed rates; reconcile item-level estimates and dates | Open |
| 15 | 3.10 | Risk P/I scores and responses, and bug severities, were not in the export and are proposed | Low | PM and PO confirm at next risk review and defect triage | Open |
| 16 | 4, 3.6.3 | Former equal 60-hour labor model conflicts with confirmed allocations | Medium | Replaced by 116 / 116 / 120 / 120 / 116 DEV hours; DOCS and meetings costed separately | Baseline corrected |